## Master (hidden)
3 WEEK LOOK-AHEAD SCHEDULE
|  |  |  | P R E V I O U S W E E K S | [20 empty] | L A S T W E E K | [6 empty] | T H I S W E E K | [6 empty] | N E X T W E E K | [6 empty] | 2 W E E K S O U T
|  |  |  | J A N U A R Y W E E K 1 | [6 empty] | J A N U A R Y W E E K 2 | [6 empty] | J A N U A R Y W E E K 3 | [6 empty] | J A N U A R Y W E E K 4 | [6 empty] | J A N U A R Y W E E K 5 | [6 empty] | F E B R U A R Y W E E K 1 | [6 empty] | F E B R U A R Y W E E K 2 | [6 empty] | NOTES | 3 W E E K S O U T | [6 empty] | 4 W E E K S O U T | [6 empty] | 5 W E E K S O U T | [6 empty] | 6 W E E K S O U T | [6 empty] | 7 W E E K S O U T | [6 empty] | 8 W E E K S O U T | [6 empty] | 9 W E E K S O U T | [6 empty] | 10 W E E K S O U T | [6 empty] | 11 W E E K S O U T | [6 empty] | 12 W E E K S O U T
|  |  | 2020-01-27 | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su |  | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su
PROJECT | AREA | % | TASK | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12 | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | 2020-01-18 | 2020-01-19 | 2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-25 | 2020-01-26 | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02 | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16 | time axis 2020-02-10 to 2020-04-19
| Aarea E |  | BMS CORE AREA E-MPOE-1&2/BDF-1&2 | bar: 2020-02-10 to 2020-02-14; 2020-02-17 to 2020-02-21; 2020-02-24 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09 to 2020-03-13; 2020-03-16 to 2020-03-20; 2020-03-23 to 2020-03-27; 2020-03-30 to 2020-04-03; 2020-04-06 to 2020-04-10; 2020-04-13 to 2020-04-17
|  | 100% | VLL3 Area E BMS Overhead Conduit
|  | 100% | VLL3 Area E BMS Wall Rough In
|  | 100% | VLL3 Area E BMS Pull Wire
|  | 100% | VLL3 Area E BMS Device Installation
|  | 100% | VLL3 Area E BMS Terminate/Label
|  | 100% | VLL3 Area E BMS QAQC L2 checklists and inspections
BMS CORE B & C AREA E ELECT RM.
|  | 100% | VLL3 Area E ER BMS Overhead Condiut
|  | 100% | VLL3 Area E ER BMS Wall Rough-In
|  | 100% | VLL3 Area E ER BMS Pull Wire
|  | 100% | VLL3 Area E ER BMS Device Installattion
|  | 100% | VLL3 Area E ER BMS Terminate/Label
|  | 98% | VLL3 Area E ER BMS QAQC L2 checklists and inspections - 1/3/2020 | [49 empty] | Part of Misc. Monitoring C, Need NCWP to complete
BMS CORE PENTHOUSE AREA E
|  | 100% | VLL3 Area E PH BMS Set Panels
|  | 100% | VLL3 Area E PH BMS Overhead Conduit
|  | 100% | VLL3 Area E PH BMS Install BMS Interconnect Conduit
|  | 100% | VLL3 Area E PH BMS Wall Rough-in
|  | 100% | VLL3 Area E PH BMS Pull Wire
|  | 100% | VLL3 Area E PH BMS Device Installattion
|  | 100% | VLL3 Area E PH BMS Terminate/Label
|  | 98% | VLL3 Area E PH BMS QAQC L2 checklists and inspections - 1/3/2020 | [49 empty] | Part of Misc. Monitoring C, Need NCWP to complete
| Aarea B |  | BMS DATA HALL MDF-B
|  | 100% | DH MDF-B BMS In Wall Rough-In
|  | 100% | DH MDF-B BMS OH Rough-In (Cold/Hot)
|  | 100% | DH MDF-B BMS Pull Wire
|  | 100% | DH MDF-B BMS Device Installattion
|  | 100% | DH MDF-B BMS Terminate/Label
|  | 100% | QAQC L2 checklists and inspections
BMS PENTHOUSE MDF-B
|  | 100% | Area MDF-B PH BMS OH Rough In (Underslab Conduit)
|  | 100% | Area MDF-B PH Install BMS Set Panels
|  | 100% | Area MDF-B PH Install BMS Branch Conduit
|  | 100% | VLL3 Area MDF-B PH BMS Pull Wire
|  | 100% | VLL3 Area MDF-B PH BMS Device Installattion
|  | 100% | VLL3 Area MDF-B PH BMS Terminate/Label
WATER ROOM A&B
VLL3 |  | 100% | VLL3 Area MDF-B PH BMS QAQC L2 checklists and inspections
|  | 100% | BMS Underground Conduit
|  | 100% | WT Area A/B BMS In Wall Rough In
|  | 100% | WT Area A/B BMS Set Water Treatment Enclosure
|  | 100% | WT Area A/B BMS OH Rough In
|  | 100% | VLL3 WT Area A/B BMS FCU and EF Controls
|  | 100% | VLL3 WT Area A/B BMS Pull Wire
|  | 100% | VLL3 WT Area A/B BMS Device Installattion
|  | 100% | VLL3 WT Area A/B BMS BMS Terminate/Label
|  | 100% | VLL3 WR Area A&B QAQC L2 checklists and inspections
BMS DATA HALL B
|  | 100% | DH B BMS In Wall Rough-In
|  | 100% | DH B BMS OH Rough-In (Cold/Hot)
|  | 100% | DH B BMS Pull Wire
|  | 100% | VLL3 DH B BMS Device Installattion
|  | 100% | VLL3 DH B BMS Terminate/Label
|  | 100% | VLL3 DH-B QAQC L2 checklists and inspections
BMS ELECTRICAL ROOM B
|  | 100% | Area B ER BMS In Wall Rough-In
|  | 100% | Area B ER BMS Set Panel Enclosures
|  | 100% | Area B ER BMS OH Rough-In
|  | 100% | VLL3 Area B ER BMS Pull Wire
|  | 100% | VLL3 Area B ER BMS Device Installattion
|  | 100% | VLL3 Area B ER BMS Terminate/Label
|  | 98% | VLL3 Area B ER BMS QAQC L2 checklists and inspections - 1/3/2020 | [49 empty] | Need NCWP to complete
BMS PENTHOUSE B
|  | 100% | Area B PH BMS OH Rough In (Underslab Conduit)
|  | 100% | Area B PH Install BMS Set Panels
|  | 100% | Area B PH Install BMS Branch Conduit
|  | 100% | VLL3 Area B PH BMS Pull Wire
|  | 100% | VLL3 Area B PH BMS Device Installattion
|  | 100% | VLL3 Area B PH BMS Terminate/Label
|  | 100% | VLL3 Area B PH QAQC L2 checklists and inspections
| Area A |  | BMS DATA HALL A
|  | 100% | DH A BMS In Wall Rough-In
|  | 100% | VLL3 DH A BMS OH Conduit Rough-In (Cold/Hot)
|  | 100% | VLL3 DH A BMS Pull Wire
|  | 100% | VLL3 DH A BMS Device Installattion
|  | 100% | VLL3 DH A BMS Terminate/Label
|  | 100% | VLL3 DH A QAQC L2 checklists and inspections
BMS ELECTRICAL ROOM A
|  | 100% | Area A ER BMS In Wall Rough-In
|  | 100% | Area A ER BMS Set Panel Enclosures
|  | 100% | VLL3 Area A ER BMS OH Rough-In
|  | 100% | VLL3 Area A ER BMS Pull Wire | [21 empty] | 2
|  | 100% | VLL3 Area A ER BMS Device Installattion
|  | 100% | VLL3 Area A ER BMS Terminate/Label | [22 empty] | 2 | 2 | 2 | 2
|  | 98% | VLL3 Area A ER BMS QAQC L2 checklists and inspections - 1/3/2020 | [24 empty] | 1 | 1
BMS PENTHOUSE A
|  | 100% | Area A PH BMS Overhead Rough In (Underslab Conduit)
|  | 100% | Area A PH BMS Set Panels
|  | 100% | VLL3 Area A PH BMS Branch Conduit
|  | 100% | VLL3 Area A PH BMS Pull Wire
|  | 100% | VLL3 Area A PH BMS Device Installattion
|  | 100% | VLL3 Area A PH BMS Terminate/Label
|  | 100% | VLL3 Area A PH BMS QAQC L2 checklists and inspections
BMS DATA HALL MDF-A
|  | 100% | DH MDF-A BMS In Wall Rough-In
|  | 100% | DH MDF-A BMS OH Rough-In (Cold/Hot)
|  | 100% | DH MDF-A BMS Pull Wire
|  | 100% | DH MDF-A BMS Device Installattion
|  | 100% | DH MDF-A BMS Terminate/Label
|  | 100% | QAQC L2 checklists and inspections
BMS PENTHOUSE MDF-A
|  | 100% | Area MDF-A PH BMS OH Rough In (Underslab Conduit)
|  | 100% | Area MDF-A PH Install BMS Set Panels
|  | 100% | Area MDF-A PH Install BMS Branch Conduit
|  | 100% | Area MDF-A PH BMS Pull Wire
|  | 100% | VLL3 Area A MDF PH BMS Device Installattion
|  | 100% | Area MDF-A PH BMS Terminate/Label
|  | 100% | QAQC L2 checklists and inspections
| Area C |  | BMS DATA HALL MDF-C
|  | 100% | DH MDF-C BMS In Wall Rough-In
|  | 100% | DH MDF-C BMS OH Rough-In (Cold/Hot)
|  | 100% | DH MDF-C BMS Pull Wire
|  | 100% | DH MDF-C BMS Device Installattion
|  | 100% | DH MDF-C BMS Terminate/Label
|  | 0% | QAQC L2 checklists and inspections - 2/20/2020 | 1 | 1 |  | 1 | 1 | [16 empty] | 1 | 1 | 1 | 1 | 1 | [16 empty] | 2 | 2 | 2 | 2 | 2 | 2
BMS PENTHOUSE MDF-C
|  | 100% | VLL3 Area C MDF PH BMS OH Rough In (Underslab Conduit)
|  | 100% | Area MDF-C PH Install BMS Set Panels
|  | 40% | Area MDF-C PH Install BMS Branch Conduit | 2 | 2 |  | 2 | 2 | [16 empty] | 2 | 2 | 2 | 2 | 2
|  | 60% | Area MDF-C PH BMS Pull Wire | [28 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  | 1
|  | 0% | Area MDF-C PH BMS Device Installattion | [28 empty] | 2 | 2 | 2 | 2 | 2 | 2 |  | 2
|  | 0% | Area MDF-C PH BMS Terminate/Label | [36 empty] | 3 | 3 | 3 | 3 | 3 |  | 3 | 3 | 3 | 3 | 3
|  | 0% | Area MDF-C PH BMS QAQC L2 checklists and inspections - 2/202020 | [46 empty] | 2 | 4
BMS DATA HALL C
|  | 100% | DH C BMS In Wall Rough-In
|  | 100% | VLL3 Area C DH BMS OH Rough-In (Cold/Hot)
|  | 100% | VLL3 Area C DH BMS Pull Wire | 2 | 2 |  | 2 | 2 |  | 8 | [13 empty] | 8
|  | 100% | VLL3 Area C DH BMS Device Installattion | 2 | 2 |  | 2 | 2 |  | 7 | [13 empty] | 7
|  | 100% | VLL3 Area C DH BMS Terminate/Label | [6 empty] | 7 | [13 empty] | 7
|  | 0% | VLL3 Area C DH BMS QAQC L2 checklists and inspections - 2/13/2020
BMS ELECTRICAL ROOM C
|  | 100% | Area C ER BMS In Wall Rough-In
|  | 100% | Area C ER BMS Set Panel Enclosures
|  | 0% | Area C ER BMS OH Rough-In | 2 | 2 |  | 2 | 2 | [16 empty] | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2
|  | 0% | Area C ER BMS Pull Wire | [32 empty] | 2 | 2 |  | 2
|  | 0% | Area C ER BMS Device Installattion | [36 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1
|  | 0% | Area C ER BMS Terminate/Label | [36 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1
|  | 0% | Area C ER BMS QAQC L2 checklists and inspections - 3/26/2020
BMS PENTHOUSE C
|  | 100% | VLL3 Area C PH BMS Overhead Rough In (Underslab Conduit)
|  | 100% | VLL3 Area C PH BMS Set Panels
|  | 90% | VLL3 Area C PH BMS Branch Conduit | [28 empty] | 4 | 4
|  | 60% | Area C PH BMS Pull Wire | 2 | 2 |  | 2 | 2 | [16 empty] | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 1
|  | 10% | Area C PH BMS Device Installattion | 2 | 2 |  | 2 | 2 | [16 empty] | 2 | 2 | 2 | 2 | 2 |  |  | 4 | 4 | 4 | 4 | 4 | 4 |  | 3
|  | 20% | Area C PH BMS Terminate/Label | [35 empty] | 5 | 2 | 2 | 2 | 2 | 2
|  | 0% | Area C PH BMS QAQC L2 checklists and inspections - 2/13/2020 | [39 empty] | 3 | 3 |  | 2 | 2 | 2 | 2
WATER ROOM C&D
|  | 100% | BMS Underground Conduit
|  | 100% | WT C/D BMS In Wall Rough In
|  | 100% | VLL3 WT C/D BMS Set Water Treatment Enclosure
|  | 60% | VLL3 WT C/D BMS OH Rough In | 3 | 3 |  | 3 | 3 | [16 empty] | 3 | 3 | 3 | 3 | 3 |  |  | 2 | 2 | 3 | 3 | 3 | 3
|  | 40% | VLL3 WT C/D BMS FCU and EF Controls
|  | 30% | VLL3 WT C/D BMS Pull Wire | [28 empty] | 4 | 4 | 4 | 4 | 4 | 4
|  | 20% | VLL3 WT C/D BMS Device Installattion | [28 empty] | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2
|  | 10% | VLL3 WT C/D BMS Terminate/Label | [30 empty] | 2 | 2 | 2 | 2 |  | 6 | 6 | 6 | 6 | 4 | 4
|  | 0% | VLL3 WT C/D BMS QAQC L2 checklists and inspections - 2/14/2020 | [39 empty] | 3 | 3 |  | 2 | 2 | 2 | 2 | 2
| Area D |  | BMS DATA HALL MDF-D
|  | 100% | VLL3 DH MDF-D BMSS In Wall Rough-In
|  | 100% | VLL3 DH MDF-D BMS OH Rough-In (Cold/Hot)
|  | 100% | VLL3 DH MDF-D BMS Pull Wire
|  | 100% | VLL3 DH MDF-D BMS Device Installattion | 1 | 1 |  | 1 | 1
|  | 100% | VLL3 DH MDF-D BMS Terminate/Label | 1 | 1 |  | 1 | 1
|  | 0% | VLL3 DH MDF-D BMS QAQC L2 checklists and inspections - 3/19/2020
BMS PENTHOUSE MDF-D
|  | 100% | VLL 3 Area D MDF PH BMS OH Rough In (Underslab Conduit)
|  | 60% | Area MDF-D PH Install BMS Set Panels
|  | 40% | VLL3 Area D MDF PH Install BMS Branch Conduit | [36 empty] | 2 | 2 | 2 |  |  |  | 2 | 2 | 2 | 2 | 2 | 2
|  | 0% | Area MDF-D PH BMS Pull Wire | [47 empty] | 1
|  | 0% | Area MDF-D PH BMS Device Installattion | [21 empty] | 2 | 2 | 2 | 2 | 2 | [21 empty] | 2
|  | 0% | Area MDF-D PH BMS Terminate/Label
|  | 0% | Area MDF-D PH BMS QAQC L2 checklists and inspections - 3/19/2020
BMS DATA HALL D
|  | 100% | DH D BMS In Wall Rough-In
|  | 100% | VLL 3 Area D DH BMS OH Rough-In (Cold/Hot) | 2 | 2 |  | 2 | 2 | [16 empty] | 2 | 2 | 2 | 2 | 2 | [10 empty] | 2 | 2 | 2 | 2 | 2 |  | 3 | 3 | 3 | 3 | 3
|  | 40% | DH D BMS Pull Wire | [21 empty] | 2 | 2 | 2 | 2 | 2 | [10 empty] | 3 | 3 | 3 | 3 | 3 |  | 4 | 4 | 4 | 4 | 4 | 4
|  | 20% | DH D BMS Device Installattion | [21 empty] | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 4 | 4 | 4 | 4 | 4 | 4
|  | 20% | DH D BMS Terminate/Label | [47 empty] | 3
|  | 0% | QAQC L2 checklists and inspections - 3/12/2020
BMS ELECTRICAL ROOM D
|  | 100% | Area D ER BMS In Wall Rough-In
|  | 0% | Area D ER BMS Set Panel Enclosures
|  | 0% | Area D ER BMS OH Rough-In | [45 empty] | 2 | 2 | 2
|  | 0% | Area D ER BMS Pull Wire
|  | 0% | Area D ER BMS Device Installattion
|  | 0% | Area D ER BMS Terminate/Label
|  | 0% | Area D ER BMS QAQC L2 checklists and inspections - 4/16/2020
BMS PENTHOUSE D
|  | 100% | Area D PH BMS Overhead Rough In (Underslab Conduit)
|  | 100% | Area D PH BMS Set Panels
|  | 0% | Area D PH BMS Branch Conduit | [30 empty] | 4 | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 2 | 2 |  | 4 | 4 | 4 | 4 | 4
|  | 0% | Area D PH BMS Pull Wire | [47 empty] | 2
|  | 0% | Area D PH BMS Device Installattion | [47 empty] | 2
|  | 0% | Area D PH BMS Terminate/Label
|  | 0% | Area D PH BMS QAQC L2 checklists and inspections - 3/12/2020
|  | 100% | Admin BMS In Wall Rough In
|  | 100% | Admin BMS OH Conduit
ADMIN 3-4 | Area 1 | 100% | Admin Area 1 BMS Pull Wire
|  | 100% | Admin Area 1 BMS Device Installattion
|  | 100% | Admin Area 1 BMS Terminate/Label
|  | 100% | Admin Area 1 QAQC L2 checklists and inspections
|  | 100% | Admin BMS In Wall Rough In
|  | 100% | Admin BMS OH Conduit
|  | 100% | Admin BMS Pull Wire
|  | 100% | Admin BMS Device Installattion
|  | 100% | Admin BMS Terminate/Label
| Area 2 | 100% | Admin Area 2 QAQC L2 checklists and inspections
|  | 100% | Admin BMS In Wall Rough In
|  | 100% | Admin BMS OH Conduit
| Area 3 | 100% | Admin Area 3 BMS Pull Wire
|  | 100% | Admin Area 3 BMS Device Installattion
|  | 100% | Admin Area 3 BMS Terminate/Label
|  | 100% | Admin Area 3 QAQC L2 checklists and inspections
|  | 100% | Admin BMS In Wall Rough In
|  | 100% | Admin BMS Set Panels
|  | 100% | Admin BMS OH Conduit
| Area 4 | 100% | Admin Area 4 BMS Pull Wire
|  | 100% | Admin Area 4 BMS Device Installattion
|  | 100% | Admin Area 4 BMS Terminate/Label
|  | 100% | Admin Area 4 QAQC L2 checklists and inspections
|  | 100% | Admin BMS In Wall Rough In
|  | 100% | Admin BMS Set Panels
|  | 100% | Admin BMS OH Conduit
| Area 5 | 100% | Admin Area 5 BMS Pull Wire
|  | 100% | Admin Area 5 BMS Device Installattion
|  | 100% | Admin Area 5 BMS Terminate/Label
|  | 100% | Admin Area 5 QAQC L2 checklists and inspections
| Area E |  | BMS CORE AREA E-MPOE-1&2/BDF-1&2
|  | 100% | Area E BMS In Wall Rough-In
|  | 100% | Area E BMS Set Panels
|  | 100% | Area E BMS Overhead Conduit
|  | 100% | Area E BMS Pull Wire
|  | 100% | Area E BMS Device Installattion
VLL 4 |  | 100% | VLL4 Area E CORE BMS Terminate/Label
|  | 100% | VLL4 Area E CORE BMS QAQC L2 checklists and inspections - 1/24/2020 | 1 | 1 |  | 1 | 1 | [16 empty] | 2 | 2 | 2 | 2 | 2
BMS CORE AREA E ELECT RM.
|  | 100% | Area E ER BMS In Wall Rough-In
|  | 100% | VLL4 Area E ER BMS OH Rough-In
|  | 100% | VLL4 Area E ER BMS Pull Wire
|  | 100% | VLL4 Area E ER BMS Device Installattion
|  | 100% | VLL 4 Area E ER BMS Terminate/Label
|  | 100% | VLL4 Area E ER BMS QAQC L2 checklists and inspections - 1/24/2020 | 1 | 1 |  | 1 | 1 | [16 empty] | 1 | 1 | 1 | 1 | 1
BMS MECHANICAL RM-AREA E
|  | 100% | MECH- E BMS In Wall Rough-In
|  | 100% | MECH- E BMS Set Panel Enclosures
|  | 100% | MECH- E BMS OH Rough-In
|  | 100% | VLL 4 Area E MECH FCU and EF Controls | 2 | 2
|  | 100% | VLL 4 Area E MECH- E BMS Pull Wire
|  | 100% | VLL 4 Area E MECH- E BMS Device Installattion
|  | 100% | VLL 4 Area E MECH- E BMS Terminate/Label
|  | 100% | VLL 4 Area E QAQC L2 checklists and inspections
| Area B |  | BMS MDF- B
|  | 100% | MDF- B BMS In Wall Rough-In
|  | 100% | MDF- B Install BMS OH
|  | 100% | VLL4 MDF- B BMS Pull Wire
|  | 100% | VLL4 MDF- B BMS Device Installattion
|  | 100% | VLL4 MDF- B BMS Terminate/Label
|  | 100% | VLL4 MDF- B BMS QAQC L2 checklists and inspections - 1/24/2020 | 1 | 1 |  | 1 | 1
WATER RM-AREA B
|  | 100% | MECH- B BMS Set Panel Enclosures
|  | 100% | VLL4 MECH- B Install BMS OH | 4 | 4 |  | 2 | 2
|  | 100% | VLL4 MECH- B BMS Pull Wire |  |  |  | 4 | 4 | [19 empty] | 2 | 2
|  | 100% | VLL4 MECH- B BMS Device Installattion | [21 empty] | 4 | 4 | 4
|  | 80% | VLL4 MECH- B BMS Terminate/Label | [21 empty] | 1 | 1 | 1 | 1 | 1
|  | 30% | VLL4 MECH- B BMS QAQC L2 checklists and inspections - 1/21/2020
BMS AREA-B ELECT RM.
|  | 100% | Area B ER BMS In Wall Rough-In
|  | 100% | VLL 4 Area B ER BMS Set Panels
|  | 100% | VLL4 Area B ER BMS OH Rough-In
|  | 95% | VLL4 Area B ER BMS Pull Wire | [21 empty] | 2 | [6 empty] | 1
|  | 100% | VLL4 Area B ER BMS Device Installattion | [22 empty] | 2
|  | 70% | VLL4 Area B ER BMS Terminate/Label | [23 empty] | 2 | [5 empty] | 1
|  | 0% | VLL4 Area B ER BMS QAQC L2 checklists and inspections - 2/4/2020
BMS DATA HALL B
|  | 100% | DH B BMS Set Panel Enclosures
|  | 100% | DH B BMS OH Rough-In (Cold/Hot)
|  | 100% | DH B BMS Conduit Rough-In
|  | 100% | VLL4 DH B BMS Pull Wire
|  | 100% | VLL4 DH B BMS Device Installattion
|  | 100% | VLL4 DH B BMS Terminate/Label
|  | 50% | VLL4 DH B BMS QAQC L2 checklists and inspections - 2/4/2020 | 1 | 1 |  | 1 | 1 | [16 empty] | 1 | 1 | 1 | 1 | 1
BMS CHILLER PADS
|  | 100% | VLL4 DH B BMS UG Rough-In
|  | 100% | VLL4 DH B BMS Conduit Rough-In
|  | 100% | VLL 4 DH B BMS Pull Wire | 2 | 2 | [22 empty] | 4 | 4
|  | 100% | VLL 4 DH B BMS Device Installattion
|  | 35% | VLL 4 DH B BMS Terminate/Label |  |  |  | 2 | 2 | [23 empty] | 1 | 2
|  | 30% | VLL 4 DH B BMS QAQC L2 checklists and inspections - 2/7/2020
VLL 5 |  |  | PRE-CONSTRUCTION
|  | 40% | VLL-5 BIM COORDINATION | [21 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
|  | 0% | VLL-5 PRE-CONSTRUCTION - Underground Conduit
VLL 5 & 6 ADMIN |  |  | PRE-CONSTRUCTION
|  | 90% | VLL 5-6 ADMIN BIM COORDINATION | [21 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
|  | 0% | VLL 5-6 ADMIN PRE-CONSTRUCTION - Underground Conduit
VLL 5 & 6 ADMIN |  |  | PRE-CONSTRUCTION
|  | 0% | VLL-6 BIM COORDINATION
|  | 0% | VLL-6 PRE-CONSTRUCTION - Underground Conduit
Cx |  |  | VLL3 Core E DEC Unit Start-up
VLL3 - B-CRU L3 (3 DAYS)
Cx |  |  | VLL3 - B-MISC MONITORING PTP (3 DAYS) | [14 empty] | 3 | 3 | 3 | 3 | 3
Cx |  |  | VLL3 - B-MISC MONITORING SOO (2 DAYS) | [14 empty] | 2 | 2 | 2 | 2 | 2
Cx |  |  | VLL3 - L4 MDF-B AHU | [7 empty] | 1 | 1
Cx |  |  | VLL3 - L4 DH-A AHU | [9 empty] | 1 | 1 | 1 |  |  | 1 | 1 | 1
Cx |  |  | VLL3 - L4 RPP 5s | [7 empty] | 1
Cx |  |  | VLL3 - L4 MSB-5/SB-5 | [7 empty] | 1
Cx |  |  | VLL3 - L4 MSB-6/SB-6 | [8 empty] | 1 | 1
Cx |  |  | VLL3 - L4 RPP 6s | [9 empty] | 1
Cx |  |  | VLL3 - L4 EG-1 (BURN) | [10 empty] | 1
Cx |  |  | VLL3 - L4 EG-1R, 4, 5, 6 (ALARMS) | [11 empty] | 1
Cx |  |  | VLL3 - L4 EG-2 (BURN) | [11 empty] | 1
Cx |  |  | VLL3 - L4 DH-B RVT | [15 empty] | 3 | 3
Cx |  |  | VLL3 - L4 DH-B CRAC UNITS, LEAK DETECTION | [17 empty] | 1
Cx |  |  | VLL3 - L4 DH-B | [17 empty] | 1
Cx |  |  | VLL3 - L4 DH-B EXHAUST FANS, UNIT HEATES | [18 empty] | 1
Cx |  |  | VLL3 - L4 EG-3 (BURN) | [14 empty] | 1
Cx |  |  | VLL3 - L4 ATS-4, 5, 6 | [14 empty] | 1
Cx |  |  | VLL3 - L4 MSB-1R/SB-1R (SOO) | [17 empty] | 1
Cx |  |  | VLL3 - DH-A LIGHTING CONTROLS | [18 empty] | 1
Cx |  |  | VLL3 - L4 MDF-A AHUs | [21 empty] | 1 | 1 | 1 | 1
Cx |  |  | VLL3 - L4 DH-A UNIT HEATERS, EXHAUST FANS, TRANSFER FANS | [25 empty] | 1
Cx |  |  | VLL3 - L4 MSB-1/SB-1 | [21 empty] | 1 | 1
Cx |  |  | VLL3 - L4 RPP-1s | [22 empty] | 1
Cx |  |  | VLL3 - L4 RPP-2s | [24 empty] | 1
Cx |  |  | VLL3 - L4 MSB-2/SB-2 | [23 empty] | 1 | 1
Cx |  |  | VLL3 - L4 MSB-3/SB-3 | [25 empty] | 1 |  |  | 1
Cx |  |  | VLL3 - L4 DH-A CRAC UNITS | [28 empty] | 1
Cx |  |  | VLL3 - L4 DH-A LEAK DETECTION | [28 empty] | 1
Cx |  |  | VLL3 - L4 RPP-3s | [28 empty] | 1
Cx |  |  | VLL3 - L4 MSB-3/SB-3 | [28 empty] | 1
Cx |  |  | VLL3 - L4 ATS-1, 2, 3 | [29 empty] | 1
Cx |  |  | VLL3 - L4 EG-1, 2, 3 | [30 empty] | 1
Cx |  |  | VLL3 - L4 DH-A RVT | [31 empty] | 1 | 1
Cx |  |  | CLEAN WEEK A & B
Cx |  |  | VLL3 - IST PREP
Cx |  |  | VLL3 - IST DH-B
Cx |  |  | VLL3 - IST DH-A
Cx |  |  | VLL3 - IST DH-A/B, CORE, ADMIN FIRE DETECTION AND SUPPRESSION
Cx |  |  | VLL3 - IST DH-A/B LIGHTING INVERTERS
Cx |  |  | VLL3 - IST DH-A/B LIGHTING CONTROLS
Cx |  |  | VLL4 - ENERGIZE WATER ROOM PANELS | [31 empty] | 2
Cx |  |  | VLL4 - L3 WATER ROOM PTP | [32 empty] | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2
Cx |  |  | VLL4 - L3 WATER ROOM SOO | bar: 2020-02-11 to 2020-02-13
Cx |  |  | VLL4 - L3 CRAH UNITS PTP | [29 empty] | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4
Cx |  |  | VLL4 - L3 CRAH UNITS SOO
Cx |  |  | VLL4 - L3 EPMS MSG-4 | [35 empty] | 1 | 1 | 1 | 1
Cx |  |  | VLL4 - L3 EPMS PTX-N1, N2
Cx |  |  | VLL4 - L3 EPMS MSB-N1, N2 | [28 empty] | 1 | 1 | 1 | 1 | 1
Cx |  |  | VLL4 - L3 EPMS STC-N1, N2
Cx |  |  | VLL4 - L3 EPMS PDU-N1- 1, 2, 3, 4, 5, 6, 7, 8 | [39 empty] | 1
Cx |  |  | VLL4 - L3 EPMS PDU-N2- 1, 2, 3, 4, 5, 6, 7, 8 | [46 empty] | 1
Cx |  |  | VLL4 - L3 EPMS UPS
Cx |  |  | VLL4 - ENERGIZE CRAH MANAGER PANELS | [32 empty] | 1
Cx |  |  | VLL4 - L3 DH-B CRAH/EXHAUST VFD PTP | [39 empty] | 4 |  |  | 4 | 4 | 4 | 4 | 4
Cx |  |  | VLL4 - L3 DH-B CRAH/EXHAUST VFD SOO
Cx |  |  | VLL4 - L3 EPMS INTEGRATION | [42 empty] | 1 | 1 | 1 | 1
Cx |  |  | VLL4 - CORE SYSTEMS TAB VERIFICATION
Cx |  |  | VLL4 - L4 MSG-4
Cx |  |  | VLL4 - L4 EG-GSB (ALARMS)
Cx |  |  | VLL4 - L4 PTX-N1, N2
Cx |  |  | VLL4 - L4 MSB-N1
Cx |  |  | VLL4 - L4 MSB-N2
Cx |  |  | VLL4 - L4 MGPC-GSB
Cx |  |  | VLL4 - L4 CHILLER PLANT
Cx |  |  | VLL4 - L4 UPS-N1A (BATTER CHARGE/ALARMS)
Cx |  |  | VLL4 - L4 STC-N1
Cx |  |  | VLL4 - L4 UPS-N1B (BATTER CHARGE/ALARMS)
Cx |  |  | VLL4 - L4 UPS-N2A (BATTER CHARGE/ALARMS)
Cx |  |  | VLL4 - L4 STC-N2
Cx |  |  | VLL4 - L4 UPS-N2B (BATTER CHARGE/ALARMS)
Cx |  |  | VLL4 - L4 UPS-N1A, N1B, N2A, N2B (SYSTEMS TESTING)
Cx |  |  | VLL4 - L4 CRAH UNITS (CORE)
Cx |  |  | VLL4 - L4 PDY-N1-1, 2,3,4,5,6,7,8
Cx |  |  | VLL4 - L4 MSB-N1
Cx |  |  | VLL4 - L4 MSB-N2
Cx |  |  | VLL4 - L4 LIGHTING INVERTER N2,N1-1E, N1-1B2
Cx |  |  | VLL4 - L4 ATS-N1/N2, N2/N1
Cx |  |  | VLL4 - L4 DH-B TAB VERIFICATION
Cx |  |  | VLL4 - L4 CRAH UNITS (DH-B)
Cx |  |  | VLL3 - BMS Area C
Cx |  |  | VLL3 - Energize Water Room BMS Panels
Cx |  |  | VLL3 - MDF-C - CVE QAQC Complete and Energization Ready
Cx |  |  | VLL3 - Water Room PTP
Cx |  |  | Water Room L3 Functional Testing
Cx |  |  | Energize PH BMS Panels
Cx |  |  | Penthouse PTP
Cx |  |  | Penthouse L3 Functional Testing (SOO Testing)
Cx |  |  | MDF-C Penthouse PTP
Cx |  |  | MDF-C L3 Functional Testing (SOO Testing)
Cx |  |  | Misc. Monitoring (LD, Efs, HT, TF, etc.) PTP
Cx |  |  | Misc. Monitoring (LD, Efs, HT, TF, etc.) L3 Functional Testing
Cx |  |  | Area C CRAC Unit L3
Cx |  |  | VLL3 - EPMS Area C
Cx |  |  | MSB EPMS Integration
Cx |  |  | RPP EPMS Integration
Cx |  |  | EG-7, 8, 9, 2R EPMS Verifications
Cx |  |  | Penthouse ATS EPMS Integration
Cx |  |  | MVS/PTX EPMS Integration
Cx |  |  | Lighting Inverters EPMS
Cx |  |  | VLL3 - Area D
Cx |  |  | DCC Ready
Cx |  |  | Penthouse BMS Control Device - CVE QAQC Complete and Energization Ready
Cx |  |  | MDF-D CVE QAQC Complete and Energization Ready
Cx |  |  | Energize DH-D PH BMS Panels
Cx |  |  | Penthouse D PTP
Cx |  |  | Penthouse D L3 Functional Testing (SOO Testing)
Cx |  |  | MDF-D Penthouse PTP
Cx |  |  | MDF-D Penthouse L3 (SOOs)
Cx |  |  | Misc. Monitoring (LD, Efs, HT, TF, etc.) PTP
Cx |  |  | Misc. Monitoring (LD, Efs, HT, TF, etc.) L3 Functional Testing
Cx |  |  | Area D CRAC Unit L3
Cx |  |  | Area C & D IST
Cx
|  |  | Headcount | 32 | 32 | 0 | 32 | 32 | 0 | 22 | 3 | 2 | 3 | 2 | 3 | 0 | 0 | 8 | 9 | 9 | 8 | 7 | 0 | 22 | 37 | 38 | 37 | 39 | 38 | 0 | 0 | 1900-02-03 | 36 | 36 | 38 | 39 | 28 | 0 | 37 | 37 | 37 | 37 | 41 | 28 | 0 | 41 | 41 | 41 | 41 | 39 | 28 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cx _ Headcount | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 3 | 0 | 0 | 8 | 9 | 9 | 8 | 7 | 0 | 0 | 2 | 3 | 2 | 3 | 2 | 0 | 0 | 6 | 6 | 6 | 8 | 9 | 0 | 0 | 7 | 7 | 7 | 7 | 11 | 0 | 0 | 11 | 11 | 11 | 11 | 9 | 0 | 0 |  | 2020-02-16: 0; 2020-02-23: 0; 2020-03-01: 0; 2020-03-08: 0; 2020-03-15: 0; 2020-03-22: 0; 2020-03-29: 0; 2020-04-05: 0; 2020-04-12: 0; 2020-04-19: 0
|  |  | CVE _ Headcount | 32 | 32 | 0 | 32 | 32 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 35 | 35 | 35 | 36 | 36 | 0 | 0 | 29 | 30 | 30 | 30 | 30 | 28 | 0 | 30 | 30 | 30 | 30 | 30 | 28 | 0 | 30 | 30 | 30 | 30 | 30 | 28 | 0
[54 empty] | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | [14 empty] | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12
[54 empty] | 2020-03-07: #VALUE!; 2020-03-08: 24; 2020-03-09: 24; 2020-03-10: 24; 2020-03-11: 24 | [36 empty] | 3 | 3 | 3 | 3 | 3
[160 empty] | 2 | 2 | 2 | 2 | 2 | bar: 2020-03-14 to 2020-03-16
[54 empty] | 2020-02-17: 4; 2020-02-18: 4; 2020-02-19: 4; 2020-02-20: 4; 2020-02-21: 4; 2020-02-24: 4; 2020-02-25: 4; 2020-02-26: 4; 2020-02-27: 4; 2020-02-28: 4; 2020-03-02: 4; 2020-03-03: 4; 2020-03-04: 4; 2020-03-07: 0; 2020-03-08: 36; 2020-03-09: 36 | [31 empty] | 1 | 1
[157 empty] | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2020-03-10 to 2020-03-11; 2020-03-14 to 2020-03-18; 2020-03-28 to 2020-04-01
1 | bar: 2020-03-02 to 2020-03-04; 2020-03-08 to 2020-03-09
1 | bar: 2020-03-02 to 2020-03-04
[156 empty] | 1 | 1
1
1 | bar: 2020-03-07 to 2020-03-09
[54 empty] | 2020-03-10: N1/N3; 2020-03-11: N2/N4 | [35 empty] | 1
1 | bar: 2020-03-07 to 2020-03-09
[54 empty] | 2020-03-10: N1; 2020-03-11: N3; 2020-03-15: N2; 2020-03-17: N4 | [37 empty] | 3 | 3
[124 empty] | X | X | X | [36 empty] | 1 | bar: 2020-02-24 to 2020-02-25; 2020-03-02 to 2020-03-04; 2020-03-07 to 2020-03-11; 2020-03-14 to 2020-03-17; 2020-03-28 to 2020-04-01
[54 empty] | 2020-02-24: 8; 2020-02-25: 8; 2020-02-26: 8; 2020-02-27: 8; 2020-02-28: 8; 2020-03-02: 8; 2020-03-03: 8; 2020-03-04: 8; 2020-03-07: 12; 2020-03-08: 12; 2020-03-09: 12; 2020-03-10: 12; 2020-03-11: 12; 2020-03-14: 12 | [39 empty] | 1
[144 empty] | X | X | [18 empty] | 1
1 | bar: 2020-02-24 to 2020-02-28; 2020-03-02 to 2020-03-04; 2020-03-07
[54 empty] | 2020-03-08: 48; 2020-03-09: 48; 2020-03-10: 48; 2020-03-11: 48; 2020-03-14: 48; 2020-03-15: 48; 2020-03-16: 48; 2020-03-17: 48; 2020-03-18: 48; 2020-03-21: 48; 2020-03-22: 48; 2020-03-23: 48; 2020-03-24: 48; 2020-03-25: 48; 2020-03-28: F | [36 empty] | 1
[54 empty] | 2020-02-17: 8; 2020-02-18: 8; 2020-02-19: 8; 2020-02-20: 8; 2020-02-21: 8; 2020-03-04: 4; 2020-03-29: S; 2020-03-30: X; 2020-03-31: X; 2020-04-01: X | X | X | X | X | X | [34 empty] | 1
[124 empty] | X | X | X | [37 empty] | 1 | bar: 2020-03-18; 2020-03-21 to 2020-03-24; 2020-03-31 to 2020-04-01
[127 empty] | X | X | X | [35 empty] | 1 | 1 | 1 | 1 | bar: 2020-03-18; 2020-03-21 to 2020-03-22
[54 empty] | 2020-02-10: 2; 2020-02-11: 2; 2020-02-12: 2; 2020-02-13: 2; 2020-02-14: 2; 2020-02-17: 1; 2020-02-18: 1; 2020-02-19: 1; 2020-02-20: 1; 2020-02-21: 1; 2020-03-02: 1; 2020-03-03: 1; 2020-03-04: 1; 2020-03-23: X; 2020-03-24: X | [6 empty] | X | X | [37 empty] | 1
[165 empty] | 1 | 1 | bar: 2020-03-08 to 2020-03-11; 2020-03-14
1 | bar: 2020-03-21 to 2020-03-25; 2020-03-28 to 2020-03-29
[141 empty] | X | [26 empty] | 1
[167 empty] | 1 | 1 | bar: 2020-03-14 to 2020-03-18
[169 empty] | 1 | 1
[126 empty] | X | [43 empty] | 1 | bar: 2020-03-16
[127 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [26 empty] | 1 | bar: 2020-03-17 to 2020-03-18; 2020-03-21 to 2020-03-25
[143 empty] | X | X | X | X | X | X | X | X | X | X | X | [16 empty] | 1
[124 empty] | X | X | X | X | X | X | [24 empty] | X | [15 empty] | 1 | bar: 2020-03-31 to 2020-04-01
[129 empty] | X | [41 empty] | 1
[124 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [33 empty] | 1 | bar: 2020-03-14 to 2020-03-18; 2020-03-21 to 2020-03-25; 2020-03-28 to 2020-04-01
[131 empty] | X | X | X | X | X | X | X | [35 empty] | 1 | 1
[94 empty] | X | X | X | X | X
[126 empty] | X | X | X | X | X | X | X | X | X | X | X | X
X
[145 empty] | X | X
[144 empty] | X | X | [22 empty] | X
[146 empty] | X | X | X | [20 empty] | 2 | 2 | 2 | 2 | 2 | 2
[144 empty] | X |  |  | X
[145 empty] | X |  | X | [23 empty] | 4 | 4 | 4 | 4
[146 empty] | X | [27 empty] | 0
[148 empty] | X | [22 empty] | 0 | 0 | 0
[170 empty] | 1 | 1 | 1 | 1 | 1
X
X
[153 empty] | X | X
X
[153 empty] | X | [20 empty] | X
X
X
[170 empty] | 0 | 0 | 0 | 0 | 0
Formulas:
T = [L A S T W E E K]+1
T = [M]+1
W = [T]+1
M = [Su]+1
R = [W]+1
F = [R]+1
Sa = [F]+1
Su = [Sa]+1

## 3-Week-Look-Ahead (hidden)
Look-A-Head Schedule
|  |  |  | WEEK ONE | [6 empty] | 2020-03-02 | [6 empty] | 2020-03-09 | [6 empty] | 2020-03-16 | [6 empty] | 2020-03-23 | [6 empty] | 2020-03-30 | [6 empty] | 2020-04-06 | [6 empty] | 2020-04-13 | [6 empty] | 2020-04-20 | [6 empty] | 2020-04-27 | [6 empty] | 2020-05-04 | [6 empty] | 2020-05-11 | [6 empty] | 2020-05-18 | [6 empty] | 2020-05-25 | [6 empty] | NOTES
|  |  |  | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su
PROJECT | AREA | TESTING | TASK | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29 | 2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-02 | 2020-05-03 | 2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-07 | 2020-05-08 | 2020-05-09 | 2020-05-10 | 2020-05-11 | 2020-05-12 | 2020-05-13 | 2020-05-14 | 2020-05-15 | 2020-05-16 | 2020-05-17 | 2020-05-18 | 2020-05-19 | 2020-05-20 | 2020-05-21 | 2020-05-22 | 2020-05-23 | 2020-05-24 | 2020-05-25 | 2020-05-26 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-05-30 | 2020-05-31
VLL3 |  |  | Retest of MPOE 1/2, CE 1/2, BDF 1/2 | M: 2; T: 2; W: 2; R: 2; F: 2; M: 0; T: 0; W: 0; R: 0; F: 0; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2
VLL3-C |  |  | EPMS - Generator Verification | bar: F; M to W
|  |  | EPMS - MSB Integration | F: 0; F: 1; M: 1; T: 1; W: 1; R: 1
EPMS - RPP Integraion | bar: T to F
EPMS - PH ATS Integration | bar: M to F; M to F; M to F; M
EPMS - MVS/PTX Integration | bar: T
EPMS - Lighting Invertors [Complete?]
|  |  | BMS - Critical Water Room PTP | T: 2; W: 2; R: 2; F: 2; M: 2
|  |  | BMS - Critical Water Room SOO | M: 1; T: 1; W: 1; R: 1; F: 1; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2
|  |  | BMS - PH PTP | M: 0; T: 0; W: 0; R: 0; F: 0; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2
|  |  | BMS - PH SOO | M: 1; T: 1; W: 1; R: 1; F: 1; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2
L4 - PH | bar: M to F
|  |  | BMS - MDF C PTP | M: 0; T: 0; W: 0; R: 0; F: 0; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2
|  |  | BMS - MDF C SOO | T: 2; W: 2; R: 2; F: 2
L4 - MDF C | bar: M to W; F; M to W
|  |  | Misc L3 - Heat Trace | M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2
|  |  | Misc L3 - Leak Detection | M: 0; T: 0; W: 0; R: 0; F: 0; M: 0; T: 0; W: 0; R: 0; F: 0; M: 0
|  |  | Misc L3 - Exhausts Fans | M: 0; T: 0; W: 0; R: 0; F: 0; M: 0; T: 0; W: 0; R: 0; F: 0; M: 0
|  |  | Misc L3 - CRAC Units | M: 0; T: 0; W: 0; R: 0; F: 0; M: 0; T: 0; W: 0; R: 0; F: 0; M: 0
|  |  | L4 - Tansfer Fans | M: 0
L4 - AC DEC 1/2 | bar: W to R
L4 Misc - LD, HT | bar: R to F
L4 EPMS - Generator Alarm Verification | bar: W
L4 EPMS - MSB | bar: M to F; M to T
L4 EPMS - RPP | bar: M to F; M to T
L4 EPMS - MVS/PTX | bar: M to F; M
|  |  | L4 EPMS -LBSB/MGPC | M: 2; T: 2; W: 2; R: 2; F: 2; W: 1
|  |  | L4 EPMS - Lighting Invertor | F: 0
L4 EPMS - Lighting Controls
RVT Area C | bar: M to T
VLL3-D |  |  | EPMS - MVS Integration | bar: R to F; R
EPMS - MSB/SB Integration | bar: M to F; F; M to R
EPMS - RPP Integraion | bar: R to F; M to W
EPMS - PH ATS Integration | bar: T to F; M
|  |  | BMS - PH D PTP | T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2
|  |  | BMS - PH D SOO | F: 2; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2
|  |  | L4 BMS - AHU Build-up | F: 2; M: 2; T: 2; W: 2; R: 2
|  |  | BMS - MDF D PTP | T: 2; W: 2; R: 2; F: 2
|  |  | BMS - MDF D SOO | M: 2; T: 2; W: 2; R: 2
|  |  | L4 BMS - MDF D | F: 2; M: 2; T: 2; W: 2
Misc L3 - D Heat Trace | bar: F; M to F; M to F; M to F; M to F; M to F; M to R
|  |  | Misc L3 - D Leak Detection | F: 0; M: 0; T: 0; W: 0; R: 0; F: 0; M: 0; T: 0; W: 0; R: 0; F: 0; M: 0; T: 0; W: 0; R: 0; F: 0; M: 0; T: 0; W: 0; R: 0; F: 0; M: 0; T: 0; W: 0; R: 0; F: 0; M: 0; T: 0; W: 0; R: 0
|  |  | Misc L3 - D Exhaust Fans | F: 0; M: 0; T: 0; W: 0; R: 0; F: 0; M: 0; T: 0; W: 0; R: 0; F: 0; M: 0; T: 0; W: 0; R: 0; F: 0; M: 0; T: 0; W: 0; R: 0; F: 0; M: 0; T: 0; W: 0; R: 0; F: 0; M: 0; T: 0; W: 0; R: 0
L4 - LD, HT, EF | bar: F
|  |  | Misc L3 - D Transfer Fans | F: 0; M: 0; T: 0; W: 0; R: 0; F: 0; M: 0; T: 0; W: 0; R: 0; F: 0; M: 1; T: 1; W: 1; R: 1; F: 1; M: 1; T: 1; W: 1; R: 1; F: 1; M: 1; T: 1; W: 1; R: 1; F: 1; M: 1; T: 1; W: 1; R: 1
L4 - Transfer Fans | bar: M
Misc L3 - D CRACs | bar: W to F; M to F; M to W
L4 EPMS - Generator Alarm Verification | bar: M
L4 EPMS - MSB | bar: W to F; M to W
|  |  | L4 EPMS - RPP | R: 2; F: 2; W: 1; R: 1; F: 1; M: 1; T: 1; W: 1
L4 EPMS - ATS/HMD | bar: R
L4 EPMS - MVS/PTX (After Hours) | bar: W
L4 EPMS - Lighting Invertor | bar: M to T
L4 EPMS - Lighting Controls | bar: W
RVT Area D | bar: R to F
VLL3 - C/D |  |  | Clean Week | M: 0; T: 0; W: 0; R: 0; F: 0; M: 0; T: 0; W: 0; R: 0; F: 0
|  |  | IST | M: 3; T: 3; W: 3; R: 3; F: 3
VLL4 - Core |  |  | BMS - Chilled Water System PTP | M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2
|  |  | BMS - Chilled Water System SOO | W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2
L4 BMS - Chilled Water System SOO | bar: M to F; M
|  |  | BMS - CRAH PTP | M: 2; T: 2; W: 2; R: 2; F: 2
|  |  | BMS - CRAH SOO | M: 0; T: 0; W: 0; R: 0; F: 0; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2
|  |  | BMS - CRAH SOO (After Chilled Water Sys) | W: 2; R: 2; F: 2; M: 2
L4 BMS - CRAH Units | bar: T to F
EPMS - PTX N1 & N2 Intergration | bar: M
EPMS - MSB N1 & N2 Integration | bar: M to T
L4 EPMS - MSB N1 & N2 | bar: T to W
L4 EPMS - MSG 4 | bar: M
|  |  | EPMS - STC N1 & N2 Integration | M: 0; T: 0
EPMS - PDU N1 1-8 | bar: M to F
EPMS - PDU N2 1-8 | bar: M to F
L4 EPMS - PDU N1 & N2 | bar: M to T
EPMS - UPS | bar: M to F
L4 EPMS - UPS (N1A, N1B, N2A, N2B) STC N1 & N2 | bar: M to R
L4 EPMS - EG GSB Alarms | bar: F
|  |  | RVT Area E | W: 0; R: 0
VLL4 - DH B |  |  | Vendor Start Up - Vertiv RPP | W: 0; R: 0; F: 0; M: 0; T: 0
|  |  | BMS - DH B CRAH PTP | M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2
|  |  | BMS - DH B CRAH SOO | M: 2; T: 2; W: 2; R: 2; F: 2; M: 2; T: 2; W: 2; R: 2; F: 2
EPMS - RPP Integraion | bar: Su; W to F; Su to W; Su; Su; Su
EPMS - SB2, SB3, MGPC-2, MGCP-3 | bar: Su; M to F; Su; Su; Su; Su
RVT Area B | bar: Su; Su; Su; Su; W to R; Su
VLL4 E & B |  |  | Clean Week | M: 0; T: 0; W: 0; R: 0; F: 0
|  |  | IST | M: 3; T: 3; W: 3; R: 3; F: 3
|  |  | Headcount | 6 | 6 | 6 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13 | 12 | 12 | 13 |  |  | 14 | 14 | 15 | 16 | 16 |  |  | 18 | 18 | 16 | 15 | 16 |  |  | 18 | 17 | 17 | 17 | 16 |  |  | 18 | 17 | 17 | 17 | 18 |  |  | 15 | 16 | 17 | 14 | 12 |  |  | 13 | 11 | 13 | 10 | 10 |  |  | 11 | 10 | 10 | 9 | 6 |  |  | 8 | 8 | 7 | 4 | 4 |  |  | 2 | 2 | 3 | 3 | 2 |  |  | 2 | 0 | 0 | 0 | 0 |  |  | 6 | 6 | 6 | 6 | 6
|  |  | Floaters (COW = 17) | [14 empty] | 5 | 4 | 5 | 5 | 4 |  |  | 3 | 3 | 2 | 1 | 1 |  |  | -1 | -1 | 1 | 2 | 1 |  |  | -1 | 0 | 0 | 0 | 1 |  |  | -1 | 0 | 0 | 0 | -1 |  |  | 2 | 1 | 0 | 3 | 5 |  |  | 4 | 6 | 4 | 7 | 7 |  |  | 6 | 7 | 7 | 8 | 11 |  |  | 9 | 9 | 10 | 13 | 13 |  |  | 15 | 15 | 14 | 14 | 15 |  |  | 15 | 17 | 17 | 17 | 17 |  |  | 11 | 11 | 11 | 11 | 11
[139 empty] | 3 | 3 | 3 | 3 | 3
[139 empty] | 2 | 2 | 2 | 2 | 2
[134 empty] | 1 | 1
[136 empty] | 1 | 1 | 1 | 1 | 1 | 1
1
1
[135 empty] | 1 | 1
1
1
1
1
[140 empty] | 3 | 3
[103 empty] | X | X | X | [36 empty] | 1
1
[123 empty] | X | X | [18 empty] | 1
1
1
[103 empty] | X | X | X | X | X | [34 empty] | 1
[103 empty] | X | X | X | [37 empty] | 1
[106 empty] | X | X | X | [35 empty] | 1 | 1 | 1 | 1
[109 empty] | X | X | [37 empty] | 1
[144 empty] | 1 | 1
1
[120 empty] | X | [26 empty] | 1
[146 empty] | 1 | 1
[148 empty] | 1 | 1
[105 empty] | X | [43 empty] | 1
[106 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [26 empty] | 1
[122 empty] | X | X | X | X | X | X | X | X | X | X | X | [16 empty] | 1
[103 empty] | X | X | X | X | X | X | [24 empty] | X | [15 empty] | 1
[108 empty] | X | [41 empty] | 1
[103 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [33 empty] | 1
[110 empty] | X | X | X | X | X | X | X | [35 empty] | 1 | 1
[105 empty] | X | X | X | X | X | X | X | X | X | X | X | X
X
[124 empty] | X | X
[123 empty] | X | X | [22 empty] | X
[125 empty] | X | X | X | [20 empty] | 2 | 2 | 2 | 2 | 2 | 2
[123 empty] | X |  |  | X
[124 empty] | X |  | X | [23 empty] | 4 | 4 | 4 | 4
[125 empty] | X | [27 empty] | 0
[127 empty] | X | [22 empty] | 0 | 0 | 0
[149 empty] | 1 | 1 | 1 | 1 | 1
X
X
[132 empty] | X | X
X
[132 empty] | X | [20 empty] | X
X
X
[149 empty] | 0 | 0 | 0 | 0 | 0

## 3-Week-Look-Ahead_W.E. 01-1 (hidden)
3 WEEK LOOK-AHEAD SCHEDULE
[6 empty] | P R E V I O U S W E E K S | [13 empty] | L A S T W E E K | [6 empty] | T H I S W E E K | [6 empty] | N E X T W E E K | [6 empty] | 2 W E E K S O U T
[6 empty] | J A N U A R Y W E E K 1 | [6 empty] | J A N U A R Y W E E K 2 | [6 empty] | J A N U A R Y W E E K 3 | [6 empty] | J A N U A R Y W E E K 4 | [6 empty] | J A N U A R Y W E E K 5 | [6 empty] | J A N U A R Y W E E K 5 | [6 empty] | NOTES | 3 W E E K S O U T | [6 empty] | 4 W E E K S O U T | [6 empty] | 5 W E E K S O U T | [6 empty] | 6 W E E K S O U T | [6 empty] | 7 W E E K S O U T | [6 empty] | 8 W E E K S O U T | [6 empty] | 9 W E E K S O U T | [6 empty] | 10 W E E K S O U T | [6 empty] | 11 W E E K S O U T | [6 empty] | 12 W E E K S O U T
[5 empty] | 2020-01-13 | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su |  | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su
PROJECT | AREA | FIELD % | SCHEDULE ID | % | TASK | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12 | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | 2020-01-18 | 2020-01-19 | 2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-25 | 2020-01-26 | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02 | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | time axis 2020-02-03 to 2020-04-12
|  | 0% | IC.A.ER.BMS.210.1 | 95% | VLL3 Area A ER BMS Pull Wire | [14 empty] | 2
|  | 0% | IC.A.ER.BMS.210.3 | 95% | VLL3 Area A ER BMS Terminate/Label | [15 empty] | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2
|  |  |  | 80% | VLL3 Area A ER BMS QAQC L2 checklists and inspections | [17 empty] | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
|  |  |  | 0% | QAQC L2 checklists and inspections | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 2 | 2 | 2 | 2
|  |  |  | 40% | Area MDF-C PH Install BMS Branch Conduit | 2 | 2 |  | 2 | 2 |  |  | 2 | 2 |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
|  |  |  | 60% | Area MDF-C PH BMS Pull Wire | [24 empty] | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 |  |  | 1
|  |  |  | 0% | Area MDF-C PH BMS Device Installattion | [24 empty] | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 |  |  | 2
|  |  |  | 0% | Area MDF-C PH BMS Terminate/Label | [36 empty] | 3 | 3 | 3 | 3
|  |  |  | 100% | VLL3 Area C DH BMS Pull Wire | 2 | 2 |  | 2 | 2 |  | 8 | 2 | 2 |  | 2 | 2 |  | 8
| Area C |  |  | 100% | VLL3 Area C DH BMS Device Installattion | 2 | 2 |  | 2 | 2 |  | 7 | 2 | 2 |  | 2 | 2 |  | 7
|  |  |  | 0% | Area C ER BMS OH Rough-In | 2 | 2 |  | 2 | 2 |  |  | 2 | 2 |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2
|  |  |  | 0% | Area C ER BMS Pull Wire | [32 empty] | 2 | 2 |  | 2
|  |  |  | 0% | Area C ER BMS Device Installattion | [36 empty] | 1 | 1 | 1 | 1
|  |  |  | 0% | Area C ER BMS Terminate/Label | [36 empty] | 1 | 1 | 1 | 1
|  | 0% | IC.C.PH.BMS.270.2 | 90% | VLL3 Area C PH BMS Branch Conduit | [21 empty] | 2 | 2 | 2 | 2 | 2 |  |  | 4 | 4
|  |  |  | 0% | Area C PH BMS Pull Wire | 2 | 2 |  | 2 | 2 |  |  | 2 | 2 |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 1
|  |  |  | 0% | Area C PH BMS Device Installattion | 2 | 2 |  | 2 | 2 |  |  | 2 | 2 |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 3
|  |  |  | 0% | Area C PH BMS Terminate/Label | [25 empty] | 2 |  |  | 3 | 3 | 3 | 3 | 3 | 3 |  | 3
|  |  |  | 0% | Area C PH BMS QAQC L2 checklists and inspections | [28 empty] | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 4 | 4
|  | 0% | WT.C/D.BMS.330.2 | 30% | VLL3 WT C/D BMS OH Rough In | 3 | 3 |  | 3 | 3 |  |  | 3 | 3 |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 3 | 3 | 3 | 3 | 3
|  |  |  | 0% | VLL3 WT C/D BMS Pull Wire | [22 empty] | 2 | 2 | 2 | 2 |  |  | 4 | 4 | 4 | 4 | 4
|  |  |  | 0% | VLL3 WT C/D BMS Device Installattion | [22 empty] | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2
|  |  |  | 0% | VLL3 WT C/D BMS Terminate/Label | [30 empty] | 2 | 2 | 2 |  |  | 6 | 6 | 6 | 6 | 6
|  |  |  | 0% | VLL3 WT C/D BMS QAQC L2 checklists and inspections | [38 empty] | 4 | 4
|  |  |  | 0% | VLL3 DH MDF-D BMS Device Installattion | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 |  | 1 | 1
|  |  |  | 0% | VLL3 DH MDF-D BMS Terminate/Label | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 |  | 1 | 1
|  |  |  | 40% | VLL3 Area D MDF PH Install BMS Branch Conduit | [36 empty] | 2 | 2 | 2 | 2
|  |  |  | 0% | Area MDF-D PH BMS Device Installattion | [14 empty] | 2 | 2 | 2 | 2 | 2
|  |  |  | 70% | VLL 3 Area D DH BMS OH Rough-In (Cold/Hot) | 2 | 2 |  | 2 | 2 |  |  | 2 | 2 |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | [17 empty] | 2 | 2 | 2 | 2
|  |  |  | 0% | DH D BMS Pull Wire | [14 empty] | 2 | 2 | 2 | 2 | 2 | [17 empty] | 3 | 3 | 3 | 3
|  |  |  | 0% | DH D BMS Device Installattion | [14 empty] | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2
|  |  |  | 85% | VLL4 Area E CORE BMS QAQC L2 checklists and inspections | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 |  | 1 | 1 |  |  | 2 | 2 | 2 | 2 | 2 | [6 empty] | 1
|  |  |  | 20% | VLL4 Area E ER BMS QAQC L2 checklists and inspections | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | [6 empty] | 2
|  |  |  | 90% | VLL 4 Area E MECH FCU and EF Controls | 2 | 2 | [5 empty] | 2 | 2 | [19 empty] | 1
|  | 0% | IC.CS.ERE.BMS.1405 | 0% | VLL 4 Area E QAQC L2 checklists and inspections | [21 empty] | 2 | 2 | 4 | 4 | 4
| Area B |  |  | 100% | VLL4 MDF- B BMS QAQC L2 checklists and inspections | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 |  | 1 | 1 | [10 empty] | 1
|  | 0% | IC.CS.MECB.BMS.2930 | 100% | VLL4 MECH- B Install BMS OH | 4 | 4 |  | 2 | 2 |  |  | 4 | 4 |  | 2 | 2
|  | 0% | IC.CS.MECB.BMS.2960.1 | 100% | VLL4 MECH- B BMS Pull Wire |  |  |  | 4 | 4 | [5 empty] | 4 | 4 | [5 empty] | 2 | 2
|  | 0% | IC.CS.MECB.BMS.2960.2 | 100% | VLL4 MECH- B BMS Device Installattion | [14 empty] | 4 | 4 | 4
|  | 0% | IC.CS.MECB.BMS.2960.3 | 80% | VLL4 MECH- B BMS Terminate/Label | [14 empty] | 1 | 1 | 1 | 1 | 1
|  | 0% | IC.CS.ERB.BMS.1430.1 | 95% | VLL4 Area B ER BMS Pull Wire | [14 empty] | 2 | [13 empty] | 1
|  | 0% | IC.CS.ERB.BMS.1430.2 | 100% | VLL4 Area B ER BMS Device Installattion | [15 empty] | 2
|  |  |  | 70% | VLL4 Area B ER BMS Terminate/Label | [16 empty] | 2 |  |  |  |  | 1 | 1 | [6 empty] | 1
|  |  |  | 0% | VLL4 Area B ER BMS QAQC L2 checklists and inspections | [35 empty] | 2 | 2
|  |  |  | 10% | VLL4 DH B BMS QAQC L2 checklists and inspections | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
|  |  |  | 25% | VLL 4 DH B BMS Pull Wire | 2 | 2 | [5 empty] | 2 | 2 | [8 empty] | 4 | 4 |  |  | 5 | 5 | 5 | 3 | 3
|  |  |  | 0% | VLL 4 DH B BMS Terminate/Label |  |  |  | 2 | 2 | [5 empty] | 2 | 2 | [9 empty] | 1 | 1 | 2 | 4 | 4 |  |  | 1 | 2
|  |  |  | 40% | VLL-5 BIM COORDINATION | [14 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
|  |  |  | 90% | VLL 5-6 ADMIN BIM COORDINATION | [14 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
Cx |  |  |  |  | VLL3 - B-MISC MONITORING PTP (3 DAYS) | [14 empty] | 3 | 3 | 3 | 3 | 3
Cx |  |  |  |  | VLL3 - B-MISC MONITORING SOO (2 DAYS) | [14 empty] | 2 | 2 | 2 | 2 | 2
Cx |  |  |  |  | VLL3 - L4 MDF-B AHU | [7 empty] | 1 | 1
Cx |  |  |  |  | VLL3 - L4 DH-A AHU | [9 empty] | 1 | 1 | 1 |  |  | 1 | 1 | 1
Cx |  |  |  |  | VLL3 - L4 RPP 5s | [7 empty] | 1
Cx |  |  |  |  | VLL3 - L4 MSB-5/SB-5 | [7 empty] | 1
Cx |  |  |  |  | VLL3 - L4 MSB-6/SB-6 | [8 empty] | 1 | 1
Cx |  |  |  |  | VLL3 - L4 RPP 6s | [9 empty] | 1
Cx |  |  |  |  | VLL3 - L4 EG-1 (BURN) | [10 empty] | 1
Cx |  |  |  |  | VLL3 - L4 EG-1R, 4, 5, 6 (ALARMS) | [11 empty] | 1
Cx |  |  |  |  | VLL3 - L4 EG-2 (BURN) | [11 empty] | 1
Cx |  |  |  |  | VLL3 - L4 DH-B RVT | [15 empty] | 3 | 3
Cx |  |  |  |  | VLL3 - L4 DH-B CRAC UNITS, LEAK DETECTION | [17 empty] | 1
Cx |  |  |  |  | VLL3 - L4 DH-B | [17 empty] | 1
Cx |  |  |  |  | VLL3 - L4 DH-B EXHAUST FANS, UNIT HEATES | [18 empty] | 1
Cx |  |  |  |  | VLL3 - L4 EG-3 (BURN) | [14 empty] | 1
Cx |  |  |  |  | VLL3 - L4 ATS-4, 5, 6 | [14 empty] | 1
Cx |  |  |  |  | VLL3 - L4 MSB-1R/SB-1R (SOO) | [17 empty] | 1
Cx |  |  |  |  | VLL3 - DH-A LIGHTING CONTROLS | [18 empty] | 1
Cx |  |  |  |  | VLL3 - L4 MDF-A AHUs | [21 empty] | 1 | 1 | 1 | 1
Cx |  |  |  |  | VLL3 - L4 DH-A UNIT HEATERS, EXHAUST FANS, TRANSFER FANS | [25 empty] | 1
Cx |  |  |  |  | VLL3 - L4 MSB-1/SB-1 | [21 empty] | 1 | 1
Cx |  |  |  |  | VLL3 - L4 RPP-1s | [22 empty] | 1
Cx |  |  |  |  | VLL3 - L4 RPP-2s | [24 empty] | 1
Cx |  |  |  |  | VLL3 - L4 MSB-2/SB-2 | [23 empty] | 1 | 1
Cx |  |  |  |  | VLL3 - L4 MSB-3/SB-3 | [25 empty] | 1 |  |  | 1
Cx |  |  |  |  | VLL3 - L4 DH-A CRAC UNITS | [28 empty] | 1
Cx |  |  |  |  | VLL3 - L4 DH-A LEAK DETECTION | [28 empty] | 1
Cx |  |  |  |  | VLL3 - L4 RPP-3s | [28 empty] | 1
Cx |  |  |  |  | VLL3 - L4 MSB-3/SB-3 | [28 empty] | 1
Cx |  |  |  |  | VLL3 - L4 ATS-1, 2, 3 | [29 empty] | 1
Cx |  |  |  |  | VLL3 - L4 EG-1, 2, 3 | [30 empty] | 1
Cx |  |  |  |  | VLL3 - L4 DH-A RVT | [31 empty] | 1 | 1
Cx |  |  |  |  | CLEAN WEEK | [35 empty] | 2 | 2 | 2 | 2 | 2
Cx |  |  |  |  | VLL4 - ENERGIZE WATER ROOM PANELS | [24 empty] | 2
Cx |  |  |  |  | VLL4 - L3 WATER ROOM PTP | [25 empty] | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2
Cx |  |  |  |  | VLL4 - L3 WATER ROOM SOO
Cx |  |  |  |  | VLL4 - L3 CRAH UNITS PTP | [29 empty] | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4
Cx |  |  |  |  | VLL4 - L3 EPMS MSG-4 | [35 empty] | 1 | 1 | 1 | 1
Cx |  |  |  |  | VLL4 - L3 EPMS MSB-N1, N2 | [28 empty] | 1 | 1 | 1 | 1 | 1
Cx |  |  |  |  | VLL4 - L3 EPMS PDU-N1- 1, 2, 3, 4, 5, 6, 7, 8 | [39 empty] | 1
Cx |  |  |  |  | VLL4 - ENERGIZE CRAH MANAGER PANELS | [32 empty] | 1
Cx |  |  |  |  | VLL4 - L3 DH-B CRAH/EXHAUST VFD PTP | [39 empty] | 4
[5 empty] | Headcount | 32 | 32 | 0 | 32 | 32 | 0 | 15 | 35 | 34 | 3 | 34 | 35 | 0 | 15 | 43 | 44 | 44 | 44 | 43 | 0 | 0 | 1900-02-01 | 39 | 39 | 43 | 45 | 3 | 0 | 46 | 46 | 41 | 41 | 44 | 7 | 0 | 35 | 35 | 35 | 39 | 37 | 0 | 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | Cx _ Headcount | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 3 | 0 | 0 | 8 | 9 | 9 | 8 | 7 | 0 | 0 | 2 | 3 | 2 | 5 | 4 | 0 | 0 | 8 | 8 | 8 | 8 | 9 | 0 | 0 | 9 | 9 | 9 | 9 | 11 | 0 | 0 |  | 2020-02-09: #REF!; 2020-02-16: #REF!; 2020-02-23: #REF!; 2020-03-01: #REF!; 2020-03-08: #REF!; 2020-03-15: #REF!; 2020-03-22: #REF!; 2020-03-29: #REF!; 2020-04-05: #REF!; 2020-04-12: #REF!
[5 empty] | CVE _ Headcount | 32 | 32 | 0 | 32 | 32 | 0 | 15 | 32 | 32 | 0 | 32 | 32 | 0 | 15 | 35 | 35 | 35 | 36 | 36 | 0 | 0 | 31 | 36 | 37 | 38 | 41 | 3 | 0 | 38 | 38 | 33 | 33 | 35 | 7 | 0 | 26 | 26 | 26 | 30 | 26 | 0 | 0
[49 empty] | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | [14 empty] | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12
[49 empty] | 2020-02-29: #VALUE!; 2020-03-01: 24; 2020-03-02: 24; 2020-03-03: 24; 2020-03-04: 24 | [36 empty] | 3 | 3 | 3 | 3 | 3
[155 empty] | 2 | 2 | 2 | 2 | 2 | bar: 2020-03-07 to 2020-03-09
[49 empty] | 2020-02-10: 4; 2020-02-11: 4; 2020-02-12: 4; 2020-02-13: 4; 2020-02-14: 4; 2020-02-17: 4; 2020-02-18: 4; 2020-02-19: 4; 2020-02-20: 4; 2020-02-21: 4; 2020-02-24: 4; 2020-02-25: 4; 2020-02-26: 4; 2020-02-29: 0; 2020-03-01: 36; 2020-03-02: 36 | [31 empty] | 1 | 1
[152 empty] | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2020-03-03 to 2020-03-04; 2020-03-07 to 2020-03-11; 2020-03-21 to 2020-03-25
1 | bar: 2020-02-24 to 2020-02-26; 2020-03-01 to 2020-03-02
1 | bar: 2020-02-24 to 2020-02-26
[151 empty] | 1 | 1
1
1 | bar: 2020-02-29 to 2020-03-02
[49 empty] | 2020-03-03: N1/N3; 2020-03-04: N2/N4 | [35 empty] | 1
1 | bar: 2020-02-29 to 2020-03-02
[49 empty] | 2020-03-03: N1; 2020-03-04: N3; 2020-03-08: N2; 2020-03-10: N4 | [37 empty] | 3 | 3
[119 empty] | X | X | X | [36 empty] | 1 | bar: 2020-02-17 to 2020-02-18; 2020-02-24 to 2020-02-26; 2020-02-29 to 2020-03-04; 2020-03-07 to 2020-03-10; 2020-03-21 to 2020-03-25
[49 empty] | 2020-02-17: 8; 2020-02-18: 8; 2020-02-19: 8; 2020-02-20: 8; 2020-02-21: 8; 2020-02-24: 8; 2020-02-25: 8; 2020-02-26: 8; 2020-02-29: 12; 2020-03-01: 12; 2020-03-02: 12; 2020-03-03: 12; 2020-03-04: 12; 2020-03-07: 12 | [39 empty] | 1
[139 empty] | X | X | [18 empty] | 1
1 | bar: 2020-02-17 to 2020-02-21; 2020-02-24 to 2020-02-26; 2020-02-29
[49 empty] | 2020-03-01: 48; 2020-03-02: 48; 2020-03-03: 48; 2020-03-04: 48; 2020-03-07: 48; 2020-03-08: 48; 2020-03-09: 48; 2020-03-10: 48; 2020-03-11: 48; 2020-03-14: 48; 2020-03-15: 48; 2020-03-16: 48; 2020-03-17: 48; 2020-03-18: 48; 2020-03-21: F | [36 empty] | 1
[49 empty] | 2020-02-10: 8; 2020-02-11: 8; 2020-02-12: 8; 2020-02-13: 8; 2020-02-14: 8; 2020-02-26: 4; 2020-03-22: S; 2020-03-23: X; 2020-03-24: X; 2020-03-25: X | X | X | X | X | X | [34 empty] | 1
[119 empty] | X | X | X | [37 empty] | 1 | bar: 2020-03-11; 2020-03-14 to 2020-03-17; 2020-03-24 to 2020-03-25
[122 empty] | X | X | X | [35 empty] | 1 | 1 | 1 | 1 | bar: 2020-03-11; 2020-03-14 to 2020-03-15
[49 empty] | 2020-02-03: 2; 2020-02-04: 2; 2020-02-05: 2; 2020-02-06: 2; 2020-02-07: 2; 2020-02-10: 1; 2020-02-11: 1; 2020-02-12: 1; 2020-02-13: 1; 2020-02-14: 1; 2020-02-24: 1; 2020-02-25: 1; 2020-02-26: 1; 2020-03-16: X; 2020-03-17: X | [6 empty] | X | X | [37 empty] | 1
[160 empty] | 1 | 1 | bar: 2020-03-01 to 2020-03-04; 2020-03-07
1 | bar: 2020-03-14 to 2020-03-18; 2020-03-21 to 2020-03-22
[136 empty] | X | [26 empty] | 1
[162 empty] | 1 | 1 | bar: 2020-03-07 to 2020-03-11
[164 empty] | 1 | 1
[121 empty] | X | [43 empty] | 1 | bar: 2020-03-09
[122 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [26 empty] | 1 | bar: 2020-03-10 to 2020-03-11; 2020-03-14 to 2020-03-18
[138 empty] | X | X | X | X | X | X | X | X | X | X | X | [16 empty] | 1
[119 empty] | X | X | X | X | X | X | [24 empty] | X | [15 empty] | 1 | bar: 2020-03-24 to 2020-03-25
[124 empty] | X | [41 empty] | 1
[119 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [33 empty] | 1 | bar: 2020-03-07 to 2020-03-11; 2020-03-14 to 2020-03-18; 2020-03-21 to 2020-03-25
[126 empty] | X | X | X | X | X | X | X | [35 empty] | 1 | 1
[89 empty] | X | X | X | X | X
[121 empty] | X | X | X | X | X | X | X | X | X | X | X | X
X
[140 empty] | X | X
[139 empty] | X | X | [22 empty] | X
[141 empty] | X | X | X | [20 empty] | 2 | 2 | 2 | 2 | 2 | 2
[139 empty] | X |  |  | X
[140 empty] | X |  | X | [23 empty] | 4 | 4 | 4 | 4
[141 empty] | X | [27 empty] | 0
[143 empty] | X | [22 empty] | 0 | 0 | 0
[165 empty] | 1 | 1 | 1 | 1 | 1
X
X
[148 empty] | X | X
X
[148 empty] | X | [20 empty] | X
X
X
[165 empty] | 0 | 0 | 0 | 0 | 0
Formulas:
M = [T]-1
Su = [L A S T W E E K]-1
T = [L A S T W E E K]+1
W = [T]+1

## 3-Week-Look-Ahead_05.11.20 (hidden)
3 WEEK LOOK-AHEAD SCHEDULE
[6 empty] | T H I S W E E K | [6 empty] | N E X T W E E K | [6 empty] | 2 W E E K S O U T
[6 empty] | M A Y W E E K 2 | [6 empty] | M A Y W E E K 3 | [6 empty] | M A Y W E E K 4 | [6 empty] | NOTES | 3 W E E K S O U T | [6 empty] | 4 W E E K S O U T | [6 empty] | 5 W E E K S O U T | [6 empty] | 6 W E E K S O U T | [6 empty] | 7 W E E K S O U T | [6 empty] | 8 W E E K S O U T | [6 empty] | 9 W E E K S O U T | [6 empty] | 10 W E E K S O U T | [6 empty] | 11 W E E K S O U T | [6 empty] | 12 W E E K S O U T
[5 empty] | 2020-05-11 | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su |  | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su
PROJECT | AREA | FIELD % | SCHEDULE ID | % | TASK | 2020-05-11 | 2020-05-12 | 2020-05-13 | 2020-05-14 | 2020-05-15 | 2020-05-16 | 2020-05-17 | 2020-05-18 | 2020-05-19 | 2020-05-20 | 2020-05-21 | 2020-05-22 | 2020-05-23 | 2020-05-24 | 2020-05-25 | 2020-05-26 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-05-30 | 2020-05-31 | time axis 2020-05-25 to 2020-08-02
VLL3 | A/B |  |  | 0% | IST |  |  | 3 | 3 | 3 | 3
[5 empty] | BIM Issues/Misc. | 2 | 2 | 1 | 1 | 1 |  |  | 1 | 1 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | Redline Panels/Label Checks
VLL3 | C |  |  | 0% | EPMS - MSB 7,8,9,2R |  | 1 | 1 | 1 | 1 |  |  | 1
|  |  |  | 0% | EPMS - RPP | [8 empty] | 1 | 1 | 1 | 1
|  |  |  | 0% | EPMS - EG-7,8,9 & 2R
|  |  |  | 0% | EPMS - PH ATS | [8 empty] | 1 | 1 | 1 | 1
|  |  |  | 50% | EPMS - MVS/PTX
|  |  |  | 0% | EPMS - Lighting Invertors
|  |  |  | 90% | BMS -MDF-C SOO | 2 | 2 | 2 | 2 | 2
|  |  |  | 99% | BMS - MISC LD (Included L4 Script) | [21 empty] | 99% BIM issues
|  |  |  | 99% | BMS - MISC HT | [21 empty] | Complete need MOP to finish work and deemed Non-essential
|  |  |  | 50% | BMS- MISC EF (IW 21 & 22) | [21 empty] | IW 22 has a BIM issue
|  |  |  | 75% | BMS - MISC CRAC (Included L4 Script) |  | 1 | 1
|  |  |  | 0% | BMS - MISC TF (Testing with Area D)
[5 empty] | L4 - C/D Water Room | [14 empty] | 2
|  |  |  | 0% | L4 - Electrical Cx | [15 empty] | 2 | 2 | 2 | 2
|  |  |  | 0% | L4 - Mechanical Cx | [15 empty] | 2 | 2 | 2 | 2
|  |  |  | 0% | C-RVT
| D |  |  | 0% | EPMS - MVS
|  |  |  | 0% | EPMS - MSB/SB | [9 empty] | 1 | 1 | 1 |  |  | 1 | 1 | 1
|  |  |  | 0% | EPMS - RPP | [17 empty] | 1 | 1
|  |  |  | 0% | EPMS - PH ATS
|  |  |  | 0% | BMS - PH PTP | [7 empty] | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4
|  |  |  | 0% | BMS - PH SOO
|  |  |  | 0% | BMS - MDF-D PTP
|  |  |  | 0% | BMS - MDF-D SOO
|  |  |  | 0% | BMS - MISC LD
|  |  |  | 0% | BMS - MSC HT
|  |  |  | 0% | BMS - MISC EF
|  |  |  | 0% | BMS - MISC TF
|  |  |  | 0% | L4 - Electrical Cx
|  |  |  | 0% | L4 - Mechanical Cx
|  |  |  | 0% | D-RVT
| C/D |  |  | 0% | IST | X | X | X | X | X |  |  | X | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | Ex. Grounding Panels
VLL4 | Core/E |  |  |  | BIM Issues/Misc.
|  |  |  | 30% | Chilled Water Sys L3 Functional Testing (chillers just to cool water via manual control) | [21 empty] | Paused testing until further notice.
|  |  |  | 0% | Chilled Water Sys L4 SOO Pre-FPT | [21 empty] | Paused testing until further notice.
|  |  |  | 100% | BMS - Core E CRAH L3 PTP
|  |  |  | 95% | BMS - Core E CRAH L3 SOO | [21 empty] | MPOE Manger SOO, PID Parameter testing, recovery testing
|  |  |  | 0% | BMS - MUA PTP | [21 empty] | Need to re test the MUA PTP. Requested vendor support from Southland
|  |  |  | 0% | BMS - MUA SOO | [21 empty] | Need to re test the MUA SOO. Requested vendor support from Southland.
|  |  |  | 20% | BMS - Humidifiers | [21 empty] | Code and graphic issues that must be resolved before completing.
|  |  |  | 20% | BMS - MME - PTP | [21 empty] | Includes Room Temperatures, Leak Detection, and mostly Heat Trace.
|  |  |  | 95% | Auxillary General Exhaust Fans | [21 empty] | Graphic issue, Need to verify with new ctz.
|  |  |  | 75% | Auxillary Leak Detection | [21 empty] | Need to trouble shoot an issue with cable breaks.
|  |  |  | 0% | Auxillary Heat Trace (2) | [21 empty] | Major code issues discovered, cannot test until code is fixed. Refer to BIM issues AF-4, JB-32, EM-122.
|  |  |  | 0% | ATS - N1/N2 | [21 empty] | Need vendor support.
|  |  |  | 0% | Battery Charger | [21 empty] | Need to schedule test date.
|  |  |  | 0% | INV N2/N1 - 1B | [21 empty] | Need to schedule test date.
|  |  |  | 100% | EPMS - PTX-N1 and N2 EPMS Integration
|  |  |  | 99% | EPMS - MSB-N1 and N2 EPMS Integration | [21 empty] | Need UPS's?
|  |  |  | 20% | EPMS - PDU-N1-1 Thu 8, and N2-1 Thru 8 Need LBs | [21 empty] | Schneider changed all the node number on the new ctz. Need to confirm if the issues are resolved.
|  |  |  | 0% | EPMS - UPS EPMS Integration | [21 empty] | Not energized?
DH-B
BIM Issues/Misc.
|  |  |  | 100% | BMS - L3 CRAH - PTP
|  |  |  | 90% | BMS - L3 CRAH - SOO | [21 empty] | Recovery checklist, MDFB Manager SOO checklsit, PID loop tuning
|  |  |  | 0% | BMS- MMA -PTP | [21 empty] | Room temperatures.
|  |  |  | 0% | BMS- MMB -PTP | [21 empty] | Room temperatures and Leak Detection points.
|  |  |  | 90% | Auxillary Leak Detection | [21 empty] | Waiting on BIM issue resolution from Schnieder and Southland. Schnieder has issued new ctz that we will verify today or tonight.
|  |  |  | 0% | Awaiting code update | [21 empty] | New CTZ received today and verifying BIM issues.
|  |  |  | 50% | EPMS - SB-2, SB-3 | [21 empty] | Pending an update from PNB. Schnieder has realesed changes in the new ctz that we need to verify.
|  |  |  | 0% | EPMS - MGPC-2, MGPC-3 | [21 empty] | Pending an update from PNB. Schnieder has realesed changes in the new ctz that we need to verify.
|  |  |  | 100% | EPMS - RPP's
|  |  |  | 0% | EPMS - MVS - 4A2 | [21 empty] | Need to schedule test date.
[5 empty] | Headcount | 4 | 6 | 8 | 7 | 7 | 3 | 0 | 6 | 9 | 11 | 11 | 11 | 0 | 0 | 11 | 13 | 13 | 13 | 13 | 0 | 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[28 empty] | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | [14 empty] | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12
[28 empty] | 2020-06-20: #VALUE!; 2020-06-21: 24; 2020-06-22: 24; 2020-06-23: 24; 2020-06-24: 24 | [36 empty] | 3 | 3 | 3 | 3 | 3
[134 empty] | 2 | 2 | 2 | 2 | 2 | bar: 2020-06-27 to 2020-06-29
[28 empty] | 2020-06-01: 4; 2020-06-02: 4; 2020-06-03: 4; 2020-06-04: 4; 2020-06-05: 4; 2020-06-08: 4; 2020-06-09: 4; 2020-06-10: 4; 2020-06-11: 4; 2020-06-12: 4; 2020-06-15: 4; 2020-06-16: 4; 2020-06-17: 4; 2020-06-20: 0; 2020-06-21: 36; 2020-06-22: 36 | [31 empty] | 1 | 1
[131 empty] | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2020-06-23 to 2020-06-24; 2020-06-27 to 2020-07-01; 2020-07-11 to 2020-07-15
1 | bar: 2020-06-15 to 2020-06-17; 2020-06-21 to 2020-06-22
1 | bar: 2020-06-15 to 2020-06-17
[130 empty] | 1 | 1
1
1 | bar: 2020-06-20 to 2020-06-22
[28 empty] | 2020-06-23: N1/N3; 2020-06-24: N2/N4 | [35 empty] | 1
1 | bar: 2020-06-20 to 2020-06-22
[28 empty] | 2020-06-23: N1; 2020-06-24: N3; 2020-06-28: N2; 2020-06-30: N4 | [37 empty] | 3 | 3
[98 empty] | X | X | X | [36 empty] | 1 | bar: 2020-06-08 to 2020-06-09; 2020-06-15 to 2020-06-17; 2020-06-20 to 2020-06-24; 2020-06-27 to 2020-06-30; 2020-07-11 to 2020-07-15
[28 empty] | 2020-06-08: 8; 2020-06-09: 8; 2020-06-10: 8; 2020-06-11: 8; 2020-06-12: 8; 2020-06-15: 8; 2020-06-16: 8; 2020-06-17: 8; 2020-06-20: 12; 2020-06-21: 12; 2020-06-22: 12; 2020-06-23: 12; 2020-06-24: 12; 2020-06-27: 12 | [39 empty] | 1
[118 empty] | X | X | [18 empty] | 1
1 | bar: 2020-06-08 to 2020-06-12; 2020-06-15 to 2020-06-17; 2020-06-20
[28 empty] | 2020-06-21: 48; 2020-06-22: 48; 2020-06-23: 48; 2020-06-24: 48; 2020-06-27: 48; 2020-06-28: 48; 2020-06-29: 48; 2020-06-30: 48; 2020-07-01: 48; 2020-07-04: 48; 2020-07-05: 48; 2020-07-06: 48; 2020-07-07: 48; 2020-07-08: 48; 2020-07-11: F | [36 empty] | 1
[28 empty] | 2020-06-01: 8; 2020-06-02: 8; 2020-06-03: 8; 2020-06-04: 8; 2020-06-05: 8; 2020-06-17: 4; 2020-07-12: S; 2020-07-13: X; 2020-07-14: X; 2020-07-15: X | X | X | X | X | X | [34 empty] | 1
[98 empty] | X | X | X | [37 empty] | 1 | bar: 2020-07-01; 2020-07-04 to 2020-07-07; 2020-07-14 to 2020-07-15
[101 empty] | X | X | X | [35 empty] | 1 | 1 | 1 | 1 | bar: 2020-07-01; 2020-07-04 to 2020-07-05
[28 empty] | 2020-05-25: 2; 2020-05-26: 2; 2020-05-27: 2; 2020-05-28: 2; 2020-05-29: 2; 2020-06-01: 1; 2020-06-02: 1; 2020-06-03: 1; 2020-06-04: 1; 2020-06-05: 1; 2020-06-15: 1; 2020-06-16: 1; 2020-06-17: 1; 2020-07-06: X; 2020-07-07: X | [6 empty] | X | X | [37 empty] | 1
[139 empty] | 1 | 1 | bar: 2020-06-21 to 2020-06-24; 2020-06-27
1 | bar: 2020-07-04 to 2020-07-08; 2020-07-11 to 2020-07-12
[115 empty] | X | [26 empty] | 1
[141 empty] | 1 | 1 | bar: 2020-06-27 to 2020-07-01
[143 empty] | 1 | 1
[100 empty] | X | [43 empty] | 1 | bar: 2020-06-29
[101 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [26 empty] | 1 | bar: 2020-06-30 to 2020-07-01; 2020-07-04 to 2020-07-08
[117 empty] | X | X | X | X | X | X | X | X | X | X | X | [16 empty] | 1
[98 empty] | X | X | X | X | X | X | [24 empty] | X | [15 empty] | 1 | bar: 2020-07-14 to 2020-07-15
[103 empty] | X | [41 empty] | 1
[98 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [33 empty] | 1 | bar: 2020-06-27 to 2020-07-01; 2020-07-04 to 2020-07-08; 2020-07-11 to 2020-07-15
[105 empty] | X | X | X | X | X | X | X | [35 empty] | 1 | 1
[68 empty] | X | X | X | X | X
[100 empty] | X | X | X | X | X | X | X | X | X | X | X | X
X
[119 empty] | X | X
[118 empty] | X | X | [22 empty] | X
[120 empty] | X | X | X | [20 empty] | 2 | 2 | 2 | 2 | 2 | 2
[118 empty] | X |  |  | X
[119 empty] | X |  | X | [23 empty] | 4 | 4 | 4 | 4
[120 empty] | X | [27 empty] | 0
[122 empty] | X | [22 empty] | 0 | 0 | 0
[144 empty] | 1 | 1 | 1 | 1 | 1
X
X
[127 empty] | X | X
X
[127 empty] | X | [20 empty] | X
X
X
[144 empty] | 0 | 0 | 0 | 0 | 0
Formulas:
T = [M]+1
Su = [Sa]+1

## 6 Week Look-Ahead
6 WEEK LOOK-AHEAD SCHEDULE
[5 empty] | T H I S W E E K | [6 empty] | N E X T W E E K | [6 empty] | 3 W E E K S O U T | [6 empty] | 4 W E E K S O U T | [6 empty] | 5 W E E K S O U T | [6 empty] | 6 W E E K S O U T | [6 empty] | NOTES
[48 empty] | 3 W E E K S O U T | [6 empty] | 4 W E E K S O U T | [6 empty] | 5 W E E K S O U T | [6 empty] | 6 W E E K S O U T | [6 empty] | 7 W E E K S O U T | [6 empty] | 8 W E E K S O U T | [6 empty] | 9 W E E K S O U T | [6 empty] | 10 W E E K S O U T | [6 empty] | 11 W E E K S O U T | [6 empty] | 12 W E E K S O U T
|  |  |  | 2025-01-27 | M | T | W | TH | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | TH | F | Sa | Su |  | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su
BUILDING | AREA/ROOM | LEVEL | MANPOWER | TASK | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | time axis 2025-02-10 to 2025-04-20
DCB1 | 1A1 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 1-10
Pull M23's Row 1-10
Pull M12's Row 1-10
FCA Gallery East
Install ICP Panels
GS.IDF.A.07
GS.IDF.A.11
Spot Leak Detectors East
| 1A1 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 11-20
Pull M23's Row 11-20
Pull M12's Row 11-20
FCA Gallery West
Spot Leak Detectors West
| 1A2 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 21-30
Pull M23's Row 21-30
Pull M12's Row 21-30
FCA Gallery East
Spot Leak Detectors East
GS.IDF.A.12
| 1A2 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 31-40
Pull M23's Row 31-40
Pull M12's Row 31-40
FCA Gallery West
Spot Leak Detectors West
| 1B1 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 1-10
Pull M23's Row 1-10
Pull M12's Row 1-10
FCA Gallery East
Install ICP Panels
GS.IDF.A.07
GS.IDF.A.11
Spot Leak Detectors East
| 1B1 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 11-20
Pull M23's Row 11-20
Pull M12's Row 11-20
FCA Gallery West
Spot Leak Detectors West
| 1B2 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 21-30
Pull M23's Row 21-30
Pull M12's Row 21-30
FCA Gallery East
Spot Leak Detectors East
GS.IDF.A.12
| 1B2 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 31-40
Pull M23's Row 31-40
Pull M12's Row 31-40
FCA Gallery West
Spot Leak Detectors West
| 1C1 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 1-10
Pull M23's Row 1-10
Pull M12's Row 1-10
FCA Gallery East
Install ICP Panels
GS.IDF.A.07
GS.IDF.A.11
Spot Leak Detectors East
| 1C1 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 11-20
Pull M23's Row 11-20
Pull M12's Row 11-20
FCA Gallery West
Spot Leak Detectors West
| 1C2 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 21-30
Pull M23's Row 21-30
Pull M12's Row 21-30
FCA Gallery East
Spot Leak Detectors East
GS.IDF.A.12
| 1C2 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 31-40
Pull M23's Row 31-40
Pull M12's Row 31-40
FCA Gallery West
Spot Leak Detectors West
| 1D1 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 1-10
Pull M23's Row 1-10
Pull M12's Row 1-10
FCA Gallery East
Install ICP Panels
GS.IDF.A.07
GS.IDF.A.11
Spot Leak Detectors East
| 1D1 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 11-20
Pull M23's Row 11-20
Pull M12's Row 11-20
FCA Gallery West
Spot Leak Detectors West
| 1D2 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 21-30
Pull M23's Row 21-30
Pull M12's Row 21-30
FCA Gallery East
Spot Leak Detectors East
GS.IDF.A.12
| 1D2 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 31-40
Pull M23's Row 31-40
Pull M12's Row 31-40
FCA Gallery West
Spot Leak Detectors West
DCB1 | 1N1/4 |  |  | FCA - Install Leak Detectors | [42 empty] | On hold due to potential damages.
|  | L2 |  | HAC - Install Humidity Transmitter
|  |  |  | Wire Pull from FCA to HACs | [42 empty] | Wrong cable installed, procuring cable/barrel connectors.
|  | L2 | 3 | FCA and Temp Sensor Terminations | x | x | x | x | x
| 1N2/3 |  |  | FCA - Install Leak Detectors | [42 empty] | On hold due to potential damages.
|  | L2 |  | HAC - Install Humidity Transmitter
|  |  |  | Wire Pull from FCA to HACs | [42 empty] | Wrong cable installed, procuring cable/barrel connectors.
|  | L2 | 3 | FCA and Temp Sensor Terminations | [7 empty] | x | x | x | x | x
| DC | L2 | 3 | Dry Cooler 7 Control Panel Conduit Tie-In (Contingent on Accessibility) |  |  | x | x | x | x
| DC | L2 | 3 | Dry Cooler 8 Control Panel Conduit Tie-In (Contingent on Accessibility) | [5 empty] | x |  | x | x | x | x
| DC | L2 | 3 | Dry Cooler 9 Control Panel Conduit Tie-In (Contingent on Accessibility) | [10 empty] | x | x | x |  | x
| DC | L2 | 3 | Dry Cooler 7 to mCUP Conduit | x | x | x
| DC | L2 | 3 | Dry Cooler 8 to mCUP Conduit |  |  |  |  | x |  |  | x | x
| DC | L2 | 3 | Dry Cooler 9 to mCUP Conduit | [7 empty] | x | x | x
| DC | L2 | 3 | Dry Cooler 1 Wire Pulls | [7 empty] | x | x | [33 empty] | Contingent on weather permiting
| DC | L2 | 3 | Dry Cooler 7 Wire Pulls | [8 empty] | x | x | [32 empty] | Contingent on weather permiting
| DC | L2 | 3 | Dry Cooler 8 Wire Pulls | [9 empty] | x | x | [31 empty] | Contingent on weather permiting
| DC | L2 | 3 | Dry Cooler 9 Wire Pulls | [10 empty] | x | x | [30 empty] | Contingent on weather permiting
| DC | L2 | 3 | Dry Cooler 1 Terminations | [14 empty] | x | x | x
| DC | L2 | 3 | Dry Cooler 7 Terminations | [14 empty] | x | x
| DC | L2 | 3 | Dry Cooler 8 Terminations | [15 empty] | x | x
| DC | L2 | 3 | Dry Cooler 9 Terminations | [17 empty] | x | x
| 1mCUP1 | L2 | 3 | Re-install Cable Tray | [42 empty] | Waiting on Brandt to install Flowmeter.
|  | L2 | 3 | Reconnecting Devices | x | x | x | x | x
|  | L2 | 3 | Re-route/ Replace Cable | [7 empty] | x | x | x | x | x |  |  | x | x
| mCUP Walkway | L2 | 4 | DP Routing MTRs (NWS/AB) | x | x | x | x | x | x
|  |  | 4 | DP Routing MTRs (NWS/CD) | [7 empty] | x | x | x | x | x | x |  | x | x | x | x | x | x
| 1mCUPX | L3 | 4 | 1mCUP2 PTP (On Temp Power) | x | x | x | x | x |  |  | x | x | x | x | x
|  |  | 4 | 1mCUP3 PTP (On Temp Power) |  |  |  |  | x |  |  | x | x | x | x | x |  |  | x | x | x | x
| N.31 | L2 | 4 | Install Cable Tray | [42 empty] | Need REI to move boxes to finish running tray.
| DHA | L2 | 4 | Install Leak Detectors | [14 empty] | x | x | x | x | x | x |  | x | x | x | x | x | x | [15 empty] | On hold due to potential damages.
Install Humidity Transmitter
| DHB | L2 | 4 | Install Overhead Supports | x | x | x | x | x | x |  | x | x | x | x | x | x |  | x | x | x | x | x | x |  | x | x | x | x | x | x |  | x | x | x | x | x | x
|  | L2 | 4 | Overhead Conduit | x | x | x | x | x | x |  | x | x | x | x | x | x |  | x | x | x | x | x | x |  | x | x | x | x | x | x |  | x | x | x | x | x | x
|  | L2 |  | Install Leak Detectors
|  | L2 |  | Install Humidity Transmitter
| DHC | L2 |  | Install Overhead Supports
|  | L2 |  | Overhead Conduit
|  | L2 |  | Install Leak Detectors
|  | L2 |  | Install Humidity Transmitter
| DHD | L2 |  | Install Overhead Supports
|  | L2 |  | Overhead Conduit
|  | L2 |  | Install Leak Detectors
|  | L2 |  | Install Humidity Transmitter
| A.10 | L2 | 3 | Install Cable Tray | x | x | x | x | x
|  | L2 |  | Pull Wire
| B.10 | L2 | 3 | Install Cable Tray | x | x | x | x | x
|  | L2 |  | Pull Wire
| C.11 | L2 |  | Install Control Panels
|  | L2 |  | Install Cable Tray
|  | L2 |  | Pull Wire
| D.14 | L2 |  | Install Control Panels
|  | L2 |  | Install Cable Tray
|  | L2 |  | Pull Wire
| SSB | L2 | 2 | Wire Control Panel | [7 empty] | x | x | [33 empty] | Waiting on parts (Light, Cards)
IWM1 |  | L2 |  | Installation
|  | L2 |  | Terminations | [42 empty] | Pending VFD Bulkhead,Heat Trace
|  | L3 | 2 | IWM PTP (On Temp Power) | x | x | x | x | x | [37 empty] | PTP must be redone per Meta, need to adjust the input range due to FTB issue.
| 1mCUP7 | L2
| 1mCUP8 | L2
| 1mCUP9 | L2
| SSB | L2 |  | Overhead/Inwall Rough-In Fire Riser Room
| SSB | L2 |  | Term Wire
| SSB | L3 |  | Program VAVs
| Site | L2 |  | Sanitary Sewer Flow Meter
| Site | L2 |  | Campus Site Flow Meter
DCB2 | 2A1 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 1-10
Pull M23's Row 1-10
Pull M12's Row 1-10
FCA Gallery East
Install ICP Panels
GS.IDF.A.07
GS.IDF.A.11
Spot Leak Detectors East
| 2A1 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 11-20
Pull M23's Row 11-20
Pull M12's Row 11-20
FCA Gallery West
Spot Leak Detectors West
| 2A2 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 21-30
Pull M23's Row 21-30
Pull M12's Row 21-30
FCA Gallery East
Spot Leak Detectors East
GS.IDF.A.12
| 2A2 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 31-40
Pull M23's Row 31-40
Pull M12's Row 31-40
FCA Gallery West
Spot Leak Detectors West
| 2B1 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 1-10
Pull M23's Row 1-10
Pull M12's Row 1-10
FCA Gallery East
Install ICP Panels
GS.IDF.A.07
GS.IDF.A.11
Spot Leak Detectors East
| 2B1 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 11-20
Pull M23's Row 11-20
Pull M12's Row 11-20
FCA Gallery West
Spot Leak Detectors West
| 2B2 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 21-30
Pull M23's Row 21-30
Pull M12's Row 21-30
FCA Gallery East
Spot Leak Detectors East
GS.IDF.A.12
| 2B2 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 31-40
Pull M23's Row 31-40
Pull M12's Row 31-40
FCA Gallery West
Spot Leak Detectors West
| 2C1 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 1-10
Pull M23's Row 1-10
Pull M12's Row 1-10
FCA Gallery East
Install ICP Panels
GS.IDF.A.07
GS.IDF.A.11
Spot Leak Detectors East
| 2C1 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 11-20
Pull M23's Row 11-20
Pull M12's Row 11-20
FCA Gallery West
Spot Leak Detectors West
| 2C2 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 21-30
Pull M23's Row 21-30
Pull M12's Row 21-30
FCA Gallery East
Spot Leak Detectors East
GS.IDF.A.12
| 1C2 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 31-40
Pull M23's Row 31-40
Pull M12's Row 31-40
FCA Gallery West
Spot Leak Detectors West
| 2D1 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 1-10
Pull M23's Row 1-10
Pull M12's Row 1-10
FCA Gallery East
Install ICP Panels
GS.IDF.A.07
GS.IDF.A.11
Spot Leak Detectors East
| 2D1 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 11-20
Pull M23's Row 11-20
Pull M12's Row 11-20
FCA Gallery West
Spot Leak Detectors West
| 2D2 |  |  | Install HAC Unistrut Row 1-10
Install HAC Unistrut Row 11-20
Install FTB Row 21-30
Pull M23's Row 21-30
Pull M12's Row 21-30
FCA Gallery East
Spot Leak Detectors East
GS.IDF.A.12
| 2D2 |  |  | Install HAC Unistrut Row 21-30
Install HAC Unistrut Row 31-40
Install FTB Row 31-40
Pull M23's Row 31-40
Pull M12's Row 31-40
FCA Gallery West
Spot Leak Detectors West
DCB2 | 002.01.A.13 | L2 | 3 | Overhead Rough-In |  |  |  |  | DEC-C (SSB) | [37 empty] | Install Leak Detection
| 002.01.B.12 | L2 | 3 | Overhead Rough-In
| 002.01.C.15 | L2 | 3 | Overhead Rough-In |  | x | x | x |  | x |  | x | x | x | x | x | x | [29 empty] | Install Leak Detection
| 002.01.C.17 | L2
| 002.01.D.16 | L2
| 002.01.D.17 | L2
IWM2 |  | L2 |  | Install
|  | L2 |  | Terminations
Admin | 100A | L2 | 3 | Overhead Rough-In | x | x | x | x | x | x |  | x | x | x | DEC-C | [31 empty] | Following behind FSG cable tray
|  | L2 |  | GS.IDF DEC-C Wire Pull
|  | L2 |  | Wire Termination
|  | L2 | 3 | Roof Conduit | [7 empty] | x | x | x |  | x |  |  | x | x
|  | L2 | 3 | Wire Pulls | [14 empty] | x | x | x | x | x |  |  | x | x | x | x | x
| 100B | L2 | 3 | Overhead Rough-In | x | x | x | x | x | x |  | x | x | x | [32 empty] | Following behind FSG cable tray
|  | L2 | 3 | Roof Conduit | [7 empty] | x | x | x |  | x |  |  | x | x
|  | L2 | 3 | Wire Pulls | [14 empty] | x | x | x | x | x |  |  | x | x | x | x | x
|  | L2 | 3 | Install Weather Station | [24 empty] | x | x
Substation 1 | MSG-A | L3/L4 | 4 | EPMS Testing | [14 empty] | x | x | x | x | x | [23 empty] | Contingent on Substation
| MSG-N | L3/L4 | 4 | EPMS Testing | [21 empty] | x | x | x | x | x | [16 empty] | Contingent on Substation
Formulas:
M = [Su]+1
T = [M]+1
W = [T]+1
TH = [W]+1
F = [TH]+1
Sa = [F]+1
Su = [Sa]+1